## README
PHI Enterprise Process Blueprint — Odoo 19 (Rev. C)
Purpose | Master blueprint of PHI processes, data and hand-offs for the Odoo 19 BRD with the implementation vendor. Companion to the published HTML blueprint and the .bpmn diagram files.
Basis | Enterprise ERP Business Reference Flow (Budget Setup). Process numbers 04, 14, 15, 16, 18, 19 come from that flow; the rest are proposed.
Key decisions reflected | Vendor proposes the Lot as the master model for each sellable unit. TORC = taxes and other related charges.
Sheets | Fit Summary · Process Catalogue · SIPOC · COPIS · Data Matrix · Master Data · Lot Touchpoints · Open Items · SOW Gap Analysis · SOW Scope Map · SOW Effort Check · SOW Observations
Yellow cells | Input columns for process owners: validation status, owner comments, decisions. Everything else is blueprint content — change it only through a revision.
Example input | Data Matrix row 09.1 → Validated = "Yes – with changes"; Owner comments = "Reservation validity is 30 days, not 15; add promo code field."
Fit legend | Standard = works out of the box · Configure = setup, Studio fields, rules · Extend = likely custom module, scope with vendor
Caveat | Odoo app placement and fit are indicative starting positions for fit-gap, not vendor commitments. Statutory items (RA 6552, PD 957, EOPT, PFRS 15) to be confirmed by Legal, Tax and the external auditor.
SOW reviewed | Achieve Without Borders SOW S343096, Odoo v19 Enterprise, vendor-signed 24 Sep 2026 (739 person-days, PHP 7,090,000 ex-VAT after discount).
Deferred scope | Leasing (10) and property management / HOA (18) are deferred to a later phase by PHI decision; they stay in the blueprint but are excluded from the SOW negotiation.

## Fit Summary
Domain | Standard | Configure | Extend | Total steps | % Extend
Plan & fund | 1 | 4 | 0 | 5 | 0%
Land | 0 | 0 | 3 | 3 | 100%
Project & inventory | 0 | 1 | 3 | 4 | 75%
Sales & leasing | 0 | 2 | 4 | 6 | 66.67%
Accounts monitoring & financing | 0 | 1 | 5 | 6 | 83.33%
Delivery & property management | 0 | 5 | 1 | 6 | 16.67%
Accounts payable | 2 | 0 | 0 | 2 | 0%
Forecasts & KPIs | 0 | 2 | 0 | 2 | 0%
Total | 3 | 15 | 16 | 34 | 47.06%
Counts come from the Data Matrix Fit column, grouped by each process's domain in Process Catalogue.

## Process Catalogue
Proc ID | Process | Value-chain stage | Domain | Accountable owner | Indicative Odoo 19 home | Fit | Numbered in reference flow? | Owner confirmed (Y/N) | Comments
01 | Budget setup (corporate & project) | Plan & fund | Plan & fund | Finance – budget & FP&A | Accounting › Budgets, Analytic plans; Approvals; Spreadsheet | Configure | Proposed
02 | Corporate & project financing | Plan & fund | Plan & fund | Treasury | Accounting (bank, loans, journals); Documents | Configure | Proposed
03 | Corporate expenses | Plan & fund | Plan & fund | Administration / requesting departments | Purchase; Approvals; Expenses; Accounting | Standard | Proposed
04 | Land acquisition | Acquire land | Land | Land acquisition / business development | Documents; Sign; Approvals; Purchase / Accounting (milestones); custom land register | Extend | Yes
05 | Project setup & project financing | Develop | Project & inventory | Project Development | Project; Accounting (analytic accounts); Documents; custom permit tracker | Configure | Proposed
06 | Project expenses & construction (milestone-based) | Develop | Project & inventory | Construction / cost control | Purchase; Project; Accounting; progress-billing extension | Extend | Proposed
07 | Inventory & financing options setup | Develop | Project & inventory | Sales admin / Project Development | Lot master model (vendor-proposed) linked to Sales products, pricelists and payment terms; Studio | Extend | Proposed
08 | Sales channel accreditation | Stock & sell | Sales & leasing | Sales admin | Contacts; Documents; Sign; Approvals; Sales commission plans | Configure | Proposed
09 | Sales (reservation to contract to sell) | Stock & sell | Sales & leasing | Sales / sales admin | CRM; Sales; Sign; Documents; Accounting; custom sales computation | Extend | Proposed
10 | Leasing | Stock & sell | Sales & leasing | Leasing / sales | Rental or Subscriptions; Sign; Accounting | Configure | Proposed
11 | Accounts monitoring (documentation, receipting, collection) | Collect & finance | Accounts monitoring & financing | Credit & collection | Accounting (invoicing, payments, follow-up); Documents; PH localization; custom amortization & penalty engine | Extend | Proposed
12 | Cancellations & return to inventory | Collect & finance | Accounts monitoring & financing | Credit & collection / Legal | Accounting; Approvals; custom Maceda calculator | Extend | Proposed
13 | Bank / Pag-IBIG takeout & in-house financing | Collect & finance | Accounts monitoring & financing | Loans & financing | Accounting; Documents; custom takeout tracker and IHF amortization | Extend | Proposed
14 | TORC – taxes and other related charges | Deliver & manage | Delivery & property management | Titling | Accounting; Approvals; Expenses (cash advance / liquidation) | Configure | Yes
15 | Unit preparation & delivery | Deliver & manage | Delivery & property management | Customer care / turnover | Field Service or Project; Sign; Helpdesk | Configure | Yes
16 | Accounts payable processing | Cross-cutting | Accounts payable | Accounting – AP | Accounting (bills, payments, batch payments); Purchase; Approvals; PH localization (2307) | Standard | Yes
17 | Commissions & sales incentives | Stock & sell | Sales & leasing | Sales admin | Sales commission plans; Purchase / Accounting (broker bills) | Extend | Proposed
18 | Property management | Deliver & manage | Delivery & property management | Property management | Subscriptions / Invoicing; Helpdesk; Field Service; Purchase | Configure | Yes
19 | Title delivery | Deliver & manage | Delivery & property management | Titling | Documents; Project (checklist); custom title tracker | Extend | Yes
X1 | Forecasts | Cross-cutting | Forecasts & KPIs | Finance – FP&A | Spreadsheet; Dashboards; Accounting reports | Configure | Proposed
X2 | KPIs & variance reports | Cross-cutting | Forecasts & KPIs | Finance – FP&A | Accounting budget reports; Spreadsheet dashboards; BI | Configure | Proposed

## SIPOC
Proc ID | Process | Suppliers | Inputs | Process steps | Outputs | Customers | Owner | Owner comments
01 | Budget setup (corporate & project) | • ManCom / Executive • Department heads • Project Development • Finance – FP&A • Treasury | • Strategic plan and targets • Prior-year actuals • Project feasibility studies • Sales, collection and cash forecasts • Chart of accounts and analytic structure | 1. Define budget structure (accounts × analytic plans: company, project, phase, cost center) 2. Annual corporate budget planning 3. Project (life-of-project) budget by phase and cost code 4. Consolidate and review 5. Approve and lock baseline; switch on budget checks | • Approved corporate budget • Approved project budget baselines • Budget-control rules • Forecast baseline | • All spending departments • Accounting and Procurement • ManCom / Board • Lenders | Finance – budget & FP&A
02 | Corporate & project financing | • Banks and lenders • Shareholders • Treasury • ManCom | • Cash-flow forecast • Approved budgets • Term sheets and loan agreements • Collateral documents | 1. Identify funding need 2. Negotiate facility; Board approval 3. Drawdown and allocate to company / project 4. Accrue and capitalize interest where allowed 5. Schedule debt service | • Loan records and amortization schedules • Funds availability per project • Interest accruals (expensed or capitalized) | • Projects • Accounts payable (loan payments) • Accounting • Lenders | Treasury
03 | Corporate expenses | • Departments (admin, branding, executive, HR) • Suppliers and service providers | • Approved department budget • Purchase requests • Quotations and contracts | 1. Raise request 2. Budget check 3. Approve 4. Issue PO or contract 5. Receive and accept 6. Send bill to AP | • POs and committed cost • Vendor bills • Expense by cost center | • Accounts payable • Accounting • Department heads | Administration / requesting departments
04 | Land acquisition | • Landowners, heirs, land brokers • Appraisers and surveyors • Legal • BIR, Registry of Deeds, LGU assessor | • Land offers • Title, tax declaration, survey, zoning • Appraisal • Acquisition budget and ManCom approval | 1. Source and log opportunity 2. Due diligence 3. Negotiate and execute agreement (deed, CTS or JV) 4. Pay per milestones 5. Pay CGT/DST/transfer tax and transfer title 6. Book land to project or land bank | • Executed agreements • Milestone payments • Title in PHI's name • Capitalized land cost; land bank record | • Project Development • Accounting • Treasury • Legal | Land acquisition / business development
05 | Project setup & project financing | • Project Development • Architects and engineers • Finance and Treasury • LGU, DENR, DHSUD | • Approved project budget • Master plan and phasing • Land title • Permits: DP, ECC, BP, CR/LTS | 1. Create project master and analytic account 2. Define phases, blocks/towers and WBS 3. Set milestones 4. Secure project financing 5. Track permits and License to Sell | • Project master data • WBS and milestones • Project funding lines • License-to-sell status | • Construction • Sales • Accounting • Inventory | Project Development
06 | Project expenses & construction (milestone-based) | • Contractors and subcontractors • Suppliers • Engineering and QS • Planning, permits, titling, marketing, sales, loan-interest cost owners | • Project budget and WBS • Contracts and BOQ • Accomplishment reports • Variation orders | 1. Award contract / issue PO 2. Verify accomplishment by milestone 3. Process progress billing with retention and recoupment 4. Send to AP 5. Update % completion | • Committed vs actual cost • % completion per unit/phase • Retention payable • Construction-in-progress cost | • Accounts payable • Accounting (POC revenue) • Inventory (unit status) • ManCom | Construction / cost control
07 | Inventory & financing options setup | • Project Development • Construction • Finance • Sales admin | • Approved subdivision / condo plans • Unit list, areas, models • Price list and escalation rules • Financing schemes | 1. Create lots as the unit master (project-phase-block-lot; tower-floor-unit for condos) 2. Set price lists 3. Track construction status: pre-construction → construction → ready 4. Track sales status: available → reserved → sold / hold / cancelled 5. Configure financing options and payment-term templates | • Sellable inventory • Price lists • Payment-term templates • Availability board | • Sales channels • Accounts monitoring • Finance | Sales admin / Project Development
08 | Sales channel accreditation | • Realty firms • Sales agents • Legal | • Accreditation application • PRC license, DHSUD registration • BIR COR (Form 2303), TIN • Accreditation agreement | 1. Receive application 2. Verify documents 3. Approve 4. Create partner record and assign commission scheme 5. Renew before expiry | • Accredited broker/agent master • Commission schemes • Validity dates | • Sales • Accounts payable (commissions) • Marketing | Sales admin
09 | Sales (reservation to contract to sell) | • Buyers and co-borrowers • Brokers and agents • Marketing • Credit & collection | • Available unit • Price list, promos, discounts • Financing scheme • Buyer KYC documents • Reservation fee | 1. Prepare sales computation 2. Reserve unit and receive reservation fee 3. Collect documents; credit check 4. Generate CTS and payment schedule 5. Sign and notarize CTS; tag unit sold | • Reservation agreement • CTS (contract to sell) • Payment schedule • Buyer master • Commission accrual | • Buyer • Accounts monitoring • Accounting • Brokers | Sales / sales admin
10 | Leasing | • Tenants • Leasing team • Legal | • Lease-available unit • Lease rate and term sheet • Security deposit, advance rent | 1. Issue term sheet 2. Approve 3. Sign lease contract 4. Bill rent, CUSA and utilities 5. Renew or terminate | • Lease contracts • Recurring invoices • Deposit liability | • Tenants • Accounting • Property management | Leasing / sales
11 | Accounts monitoring (documentation, receipting, collection) | • Buyers • Cashier • Sales admin • Banks (PDCs, transfers) | • Signed CTS and payment schedule • Payments: cash, check, PDC, bank transfer, online • Buyer documents | 1. Manage contracts and documents 2. Issue BIR-compliant invoice / receipt 3. Post and allocate collections 4. Issue SOA 5. Compute delinquency and penalties 6. Produce aging | • Posted collections • Invoices / receipts • SOA • Penalties and aging • Delinquency list | • Buyers • Accounting • Treasury • ManCom | Credit & collection
12 | Cancellations & return to inventory | • Buyer (voluntary) • Credit & collection (default) • Legal | • Cancellation request or default status • Payment history • Years of installments paid | 1. Observe grace period 2. Serve notarial notice 3. Compute cash surrender value or forfeiture 4. Approve 5. Reverse receivable, revenue and commission 6. Refund via AP; return unit | • Cancellation record • Refund payable or forfeiture income • Unit back to available | • Buyer • Accounts payable • Accounting • Sales / inventory | Credit & collection / Legal
13 | Bank / Pag-IBIG takeout & in-house financing | • Buyer • Banks and Pag-IBIG • Titling | • Equity fully paid • Loan requirements • Letter of guaranty / notice of approval • Title and DOAS | 1. Takeout: collect requirements, submit, receive decision, release documents, collect proceeds 2. IHF: approve, set amortization with interest, collect monthly | • Loan proceeds applied • Closed buyer balance or IHF receivable • Interest income | • Accounts monitoring • Treasury • Accounting • Titling | Loans & financing
14 | TORC – taxes and other related charges | • Titling • BIR, LGU, Registry of Deeds | • Deed of absolute sale • Computation of taxes (DST, transfer tax) and other related charges (registration, notarial, processing fees) • TORC budget | 1. Compute 2. Approve against budget 3. Fund cash advance or bill 4. Pay agencies 5. Liquidate 6. Charge to buyer or project | • Paid TORC • Liquidation • Recoverable charges on buyer ledger | • Accounts payable • Title delivery • Accounting | Titling
15 | Unit preparation & delivery | • Construction and QA • Credit & collection • Buyer | • Ready-for-occupancy unit • Turnover eligibility (payment status) • Punch list | 1. Check eligibility 2. Schedule joint inspection 3. Rectify defects 4. Sign acceptance; hand over keys 5. Start warranty | • Certificate of acceptance • Warranty period • Unit status: turned over | • Buyer • Property management • Accounting | Customer care / turnover
16 | Accounts payable processing | • Corporate, land, project, sales, TORC and property-management expense owners • Loan servicing • Suppliers, contractors, brokers | • Vendor bills • PO and receipts / accomplishment • Withholding tax codes | 1. Capture invoice 2. Match and validate 3. Budget check 4. Approve per DOA 5. Compute EWT; schedule payment 6. Disburse; issue BIR 2307 | • Payments • BIR 2307 certificates • AP aging • Actuals against budget | • Suppliers • Treasury • Accounting • BIR | Accounting – AP
17 | Commissions & sales incentives | • Sales • Brokers and agents • Accounts monitoring | • Signed CTS • Collection % per account • Commission scheme and release tranches • Non-cash incentive programs | 1. Accrue on sale 2. Release by tranche when collection thresholds are hit 3. Compute splits and EWT 4. Approve 5. Pay via AP | • Commission payable • Released commissions • Non-cash incentives issued | • Brokers and agents • Accounts payable • Accounting | Sales admin
18 | Property management | • Turnover • Homeowners • HOA • Utilities and service vendors | • Turned-over units • Dues rates • Service requests • Vendor bills | 1. Onboard homeowner 2. Bill and collect dues 3. Service requests and maintenance 4. Process bills and expenses 5. Turn over to HOA | • Dues invoices • Service tickets • PM expenses • HOA turnover package | • Homeowners • HOA • Accounts payable • Accounting | Property management
19 | Title delivery | • Titling • Legal • BIR, Registry of Deeds, assessor • Bank / Pag-IBIG | • Full payment or takeout • DOAS • Mother title / condo title • TORC paid | 1. Prepare documents 2. Pay fees and taxes 3. Process eCAR and transfer 4. Update tax declaration 5. Release to buyer or lender | • TCT/CCT in buyer's name • Tax declaration • Delivery acknowledgment | • Buyer • Bank / Pag-IBIG • Accounts monitoring | Titling
X1 | Forecasts | • Sales • Credit & collection • Construction • Treasury | • Pipeline and reservations • Collection schedules • Cost-to-complete • Loan schedules | 1. Refresh monthly 2. Roll forward 3. Compare to budget 4. Publish | • Sales, collection, cost and cash forecasts | • ManCom • Treasury • Lenders | Finance – FP&A
X2 | KPIs & variance reports | • All processes | • Budgets and actuals by analytic account • Sales and collection data • Construction progress | 1. Close period 2. Compute KPIs 3. Explain variances 4. Review with owners | • Budget vs actual • Absorption and sales velocity • Collection efficiency and aging • Cost variance | • ManCom • Board • Process owners | Finance – FP&A

## COPIS
COPIS — customer-first view of each process
Same content as SIPOC, read from the customer backwards: who is served, what they receive, how it is produced, what it needs, and who supplies it.
Proc ID | Process | Customers | Outputs | Process steps | Inputs | Suppliers | Customer requirement (validate with customer)
L0 | Enterprise (PHI) | • Homebuyers and co-borrowers • Tenants • Homeowners' associations • Shareholders and ManCom • Lenders, regulators, auditors | • Completed houses, lots and condo units • Titles in buyers' names • Managed communities, HOA turnover • Collections, revenue, returns • Statutory reports and BIR filings | 1. Plan & fund 2. Acquire land 3. Develop 4. Stock & sell 5. Collect & finance 6. Deliver & manage 7. Pay & measure | • Land and titles • Capital and loans • Materials, labor, permits • Market demand, buyer payments • Policies and regulations | • Landowners, JV partners • Banks, Pag-IBIG, shareholders • Contractors and suppliers • Accredited brokers and agents • BIR, RD, LGUs, DHSUD, DENR
01 | Budget setup (corporate & project) | • All spending departments • Accounting and Procurement • ManCom / Board • Lenders | • Approved corporate budget • Approved project budget baselines • Budget-control rules • Forecast baseline | 1. Define budget structure (accounts × analytic plans: company, project, phase, cost center) 2. Annual corporate budget planning 3. Project (life-of-project) budget by phase and cost code 4. Consolidate and review 5. Approve and lock baseline; switch on budget checks | • Strategic plan and targets • Prior-year actuals • Project feasibility studies • Sales, collection and cash forecasts • Chart of accounts and analytic structure | • ManCom / Executive • Department heads • Project Development • Finance – FP&A • Treasury
02 | Corporate & project financing | • Projects • Accounts payable (loan payments) • Accounting • Lenders | • Loan records and amortization schedules • Funds availability per project • Interest accruals (expensed or capitalized) | 1. Identify funding need 2. Negotiate facility; Board approval 3. Drawdown and allocate to company / project 4. Accrue and capitalize interest where allowed 5. Schedule debt service | • Cash-flow forecast • Approved budgets • Term sheets and loan agreements • Collateral documents | • Banks and lenders • Shareholders • Treasury • ManCom
03 | Corporate expenses | • Accounts payable • Accounting • Department heads | • POs and committed cost • Vendor bills • Expense by cost center | 1. Raise request 2. Budget check 3. Approve 4. Issue PO or contract 5. Receive and accept 6. Send bill to AP | • Approved department budget • Purchase requests • Quotations and contracts | • Departments (admin, branding, executive, HR) • Suppliers and service providers
04 | Land acquisition | • Project Development • Accounting • Treasury • Legal | • Executed agreements • Milestone payments • Title in PHI's name • Capitalized land cost; land bank record | 1. Source and log opportunity 2. Due diligence 3. Negotiate and execute agreement (deed, CTS or JV) 4. Pay per milestones 5. Pay CGT/DST/transfer tax and transfer title 6. Book land to project or land bank | • Land offers • Title, tax declaration, survey, zoning • Appraisal • Acquisition budget and ManCom approval | • Landowners, heirs, land brokers • Appraisers and surveyors • Legal • BIR, Registry of Deeds, LGU assessor
05 | Project setup & project financing | • Construction • Sales • Accounting • Inventory | • Project master data • WBS and milestones • Project funding lines • License-to-sell status | 1. Create project master and analytic account 2. Define phases, blocks/towers and WBS 3. Set milestones 4. Secure project financing 5. Track permits and License to Sell | • Approved project budget • Master plan and phasing • Land title • Permits: DP, ECC, BP, CR/LTS | • Project Development • Architects and engineers • Finance and Treasury • LGU, DENR, DHSUD
06 | Project expenses & construction (milestone-based) | • Accounts payable • Accounting (POC revenue) • Inventory (unit status) • ManCom | • Committed vs actual cost • % completion per unit/phase • Retention payable • Construction-in-progress cost | 1. Award contract / issue PO 2. Verify accomplishment by milestone 3. Process progress billing with retention and recoupment 4. Send to AP 5. Update % completion | • Project budget and WBS • Contracts and BOQ • Accomplishment reports • Variation orders | • Contractors and subcontractors • Suppliers • Engineering and QS • Planning, permits, titling, marketing, sales, loan-interest cost owners
07 | Inventory & financing options setup | • Sales channels • Accounts monitoring • Finance | • Sellable inventory • Price lists • Payment-term templates • Availability board | 1. Create lots as the unit master (project-phase-block-lot; tower-floor-unit for condos) 2. Set price lists 3. Track construction status: pre-construction → construction → ready 4. Track sales status: available → reserved → sold / hold / cancelled 5. Configure financing options and payment-term templates | • Approved subdivision / condo plans • Unit list, areas, models • Price list and escalation rules • Financing schemes | • Project Development • Construction • Finance • Sales admin
08 | Sales channel accreditation | • Sales • Accounts payable (commissions) • Marketing | • Accredited broker/agent master • Commission schemes • Validity dates | 1. Receive application 2. Verify documents 3. Approve 4. Create partner record and assign commission scheme 5. Renew before expiry | • Accreditation application • PRC license, DHSUD registration • BIR COR (Form 2303), TIN • Accreditation agreement | • Realty firms • Sales agents • Legal
09 | Sales (reservation to contract to sell) | • Buyer • Accounts monitoring • Accounting • Brokers | • Reservation agreement • CTS (contract to sell) • Payment schedule • Buyer master • Commission accrual | 1. Prepare sales computation 2. Reserve unit and receive reservation fee 3. Collect documents; credit check 4. Generate CTS and payment schedule 5. Sign and notarize CTS; tag unit sold | • Available unit • Price list, promos, discounts • Financing scheme • Buyer KYC documents • Reservation fee | • Buyers and co-borrowers • Brokers and agents • Marketing • Credit & collection
10 | Leasing | • Tenants • Accounting • Property management | • Lease contracts • Recurring invoices • Deposit liability | 1. Issue term sheet 2. Approve 3. Sign lease contract 4. Bill rent, CUSA and utilities 5. Renew or terminate | • Lease-available unit • Lease rate and term sheet • Security deposit, advance rent | • Tenants • Leasing team • Legal
11 | Accounts monitoring (documentation, receipting, collection) | • Buyers • Accounting • Treasury • ManCom | • Posted collections • Invoices / receipts • SOA • Penalties and aging • Delinquency list | 1. Manage contracts and documents 2. Issue BIR-compliant invoice / receipt 3. Post and allocate collections 4. Issue SOA 5. Compute delinquency and penalties 6. Produce aging | • Signed CTS and payment schedule • Payments: cash, check, PDC, bank transfer, online • Buyer documents | • Buyers • Cashier • Sales admin • Banks (PDCs, transfers)
12 | Cancellations & return to inventory | • Buyer • Accounts payable • Accounting • Sales / inventory | • Cancellation record • Refund payable or forfeiture income • Unit back to available | 1. Observe grace period 2. Serve notarial notice 3. Compute cash surrender value or forfeiture 4. Approve 5. Reverse receivable, revenue and commission 6. Refund via AP; return unit | • Cancellation request or default status • Payment history • Years of installments paid | • Buyer (voluntary) • Credit & collection (default) • Legal
13 | Bank / Pag-IBIG takeout & in-house financing | • Accounts monitoring • Treasury • Accounting • Titling | • Loan proceeds applied • Closed buyer balance or IHF receivable • Interest income | 1. Takeout: collect requirements, submit, receive decision, release documents, collect proceeds 2. IHF: approve, set amortization with interest, collect monthly | • Equity fully paid • Loan requirements • Letter of guaranty / notice of approval • Title and DOAS | • Buyer • Banks and Pag-IBIG • Titling
14 | TORC – taxes and other related charges | • Accounts payable • Title delivery • Accounting | • Paid TORC • Liquidation • Recoverable charges on buyer ledger | 1. Compute 2. Approve against budget 3. Fund cash advance or bill 4. Pay agencies 5. Liquidate 6. Charge to buyer or project | • Deed of absolute sale • Computation of taxes (DST, transfer tax) and other related charges (registration, notarial, processing fees) • TORC budget | • Titling • BIR, LGU, Registry of Deeds
15 | Unit preparation & delivery | • Buyer • Property management • Accounting | • Certificate of acceptance • Warranty period • Unit status: turned over | 1. Check eligibility 2. Schedule joint inspection 3. Rectify defects 4. Sign acceptance; hand over keys 5. Start warranty | • Ready-for-occupancy unit • Turnover eligibility (payment status) • Punch list | • Construction and QA • Credit & collection • Buyer
16 | Accounts payable processing | • Suppliers • Treasury • Accounting • BIR | • Payments • BIR 2307 certificates • AP aging • Actuals against budget | 1. Capture invoice 2. Match and validate 3. Budget check 4. Approve per DOA 5. Compute EWT; schedule payment 6. Disburse; issue BIR 2307 | • Vendor bills • PO and receipts / accomplishment • Withholding tax codes | • Corporate, land, project, sales, TORC and property-management expense owners • Loan servicing • Suppliers, contractors, brokers
17 | Commissions & sales incentives | • Brokers and agents • Accounts payable • Accounting | • Commission payable • Released commissions • Non-cash incentives issued | 1. Accrue on sale 2. Release by tranche when collection thresholds are hit 3. Compute splits and EWT 4. Approve 5. Pay via AP | • Signed CTS • Collection % per account • Commission scheme and release tranches • Non-cash incentive programs | • Sales • Brokers and agents • Accounts monitoring
18 | Property management | • Homeowners • HOA • Accounts payable • Accounting | • Dues invoices • Service tickets • PM expenses • HOA turnover package | 1. Onboard homeowner 2. Bill and collect dues 3. Service requests and maintenance 4. Process bills and expenses 5. Turn over to HOA | • Turned-over units • Dues rates • Service requests • Vendor bills | • Turnover • Homeowners • HOA • Utilities and service vendors
19 | Title delivery | • Buyer • Bank / Pag-IBIG • Accounts monitoring | • TCT/CCT in buyer's name • Tax declaration • Delivery acknowledgment | 1. Prepare documents 2. Pay fees and taxes 3. Process eCAR and transfer 4. Update tax declaration 5. Release to buyer or lender | • Full payment or takeout • DOAS • Mother title / condo title • TORC paid | • Titling • Legal • BIR, Registry of Deeds, assessor • Bank / Pag-IBIG
X1 | Forecasts | • ManCom • Treasury • Lenders | • Sales, collection, cost and cash forecasts | 1. Refresh monthly 2. Roll forward 3. Compare to budget 4. Publish | • Pipeline and reservations • Collection schedules • Cost-to-complete • Loan schedules | • Sales • Credit & collection • Construction • Treasury
X2 | KPIs & variance reports | • ManCom • Board • Process owners | • Budget vs actual • Absorption and sales velocity • Collection efficiency and aging • Cost variance | 1. Close period 2. Compute KPIs 3. Explain variances 4. Review with owners | • Budgets and actuals by analytic account • Sales and collection data • Construction progress | • All processes

## Data Matrix
Ref | Proc ID | Process | Step | a. Trigger event | b. Inputs & data fields | c. System hand-off | d. Exceptions / edge cases | Fit | Owner | Validated | Owner comments
01.1 | 01 | Budget setup (corporate & project) | Define budget structure | Budget cycle opens (timer, prior-year Q3) | Fiscal year; company; account; analytic plans (business unit, project, phase, cost center, expense type); budget version; currency | Accounting › Analytic plans → Budgets; templates out to Spreadsheet | New project mid-year needs lines; COA changes after load; intercompany charges across PHI entities | Configure | Finance – budget & FP&A
01.2 | 01 | Budget setup (corporate & project) | Corporate budget approval | Templates issued to departments | Department; account; monthly amounts; justification; prior-year actual; version; approver; approval date | Spreadsheet import → Budget (draft) → Approvals → Budget (confirmed) → budget check on PR/PO/bill | Realignment between lines; supplemental budget; rejected versions kept for audit; approved over-budget override | Configure | Finance – budget & FP&A
01.3 | 01 | Budget setup (corporate & project) | Project (life-of-project) budget | Project approved on feasibility, or new phase launched | Project; phase; cost code; categories (land, planning, permits, titling, construction by milestone, marketing, sales, loan interest); contingency %; revenue forecast (units × price) | Project Development → Budget on project analytic → Project WBS; baseline snapshot kept for variance | Budgets spanning several fiscal years; re-baseline after scope change; price escalation; overrun beyond contingency | Configure | Finance – budget & FP&A
02.1 | 02 | Corporate & project financing | Loan drawdown & allocation | Loan agreement signed; approved funding requirement | Lender; facility; principal; fixed/floating rate; tenor; drawdown date; amortization schedule; collateral; project allocation; capitalize-interest flag | Treasury → Accounting (loan liability, interest accrual) → project analytic (capitalized interest) → AP (debt-service schedule) | Repricing; prepayment penalties; stop capitalizing interest at completion; covenant breach | Configure | Treasury
03.1 | 03 | Corporate expenses | Corporate expense request | Department need arises | Requester; cost center; category (branding, admin, departmental, executive); amount; budget line; vendor; attachments | Purchase request / Approvals → budget check → PO → vendor bill (16) | Unbudgeted urgent spend; recurring contracts (utilities, subscriptions); petty cash and reimbursements via Expenses | Standard | Administration / requesting departments
04.1 | 04 | Land acquisition | Land due diligence | Land opportunity logged | Owner(s); location; OCT/TCT no.; lot area; tax declaration no.; zoning; encumbrances; appraised value; asking price; broker | Custom land register + Documents workspace → Approvals to ManCom | Title defects or adverse claims; multiple heirs (extrajudicial settlement); CARP/DAR coverage; informal settlers | Extend | Land acquisition / business development
04.2 | 04 | Land acquisition | Land agreement & milestone payments | ManCom approval | Agreement type (deed of sale, CTS, JV); price; milestones (condition, date, %); taxes borne by; JV sharing ratio | Sign → vendor bill per milestone → AP (16) → Accounting (land held for development / advances) | JV landowner paid in units (non-cash, inventory allocation); unmet milestone conditions; renegotiation; installment interest | Extend | Land acquisition / business development
04.3 | 04 | Land acquisition | Titling with fees | Final payment made; deed notarized | CGT; DST; transfer tax; registration fees; eCAR no.; new TCT no.; dates | Fees → AP; TCT no. → land register and project master; land cost capitalized to project analytic | Who shoulders taxes; late-filing surcharges; consolidation or subdivision of titles before development | Extend | Land acquisition / business development
05.1 | 05 | Project setup & project financing | Project setup | Land titled and project budget approved | Project code; name; company; location; type (horizontal / vertical); phases; blocks or towers; WBS; analytic account; permits (DP, ECC, BP, CR/LTS) | Project ↔ analytic account ↔ Budget; permit tracker; releases to unit creation (07.1) | Project across entities or JV; phasing changes; no LTS means no selling — system must block reservations | Configure | Project Development
06.1 | 06 | Project expenses & construction (milestone-based) | Construction contract & progress billing | Contract awarded; accomplishment report submitted | Contractor; contract amount; BOQ / cost code; downpayment %; retention %; progress %; cumulative billed; recoupment; variation orders; EWT | Purchase (contract/PO) → Project milestone % → vendor bill with retention and recoupment → AP; % completion → unit construction status and POC revenue | Variation orders; liquidated damages; back-charges; retention release after defects liability period; owner-furnished materials | Extend | Construction / cost control
07.1 | 07 | Inventory & financing options setup | Lot master creation & pricing | Project released for sale (LTS issued) | Lot ID (project-phase-block-lot; tower-floor-unit for condos); house model; lot and floor area; list price / TCP; price per sqm; VAT treatment; parking; construction status; sales status; mother / derivative title | Lot master (vendor-proposed) ↔ product and pricelist ↔ project analytic; availability board to CRM and brokers; every downstream document (reservation, CTS, ledger, turnover, title) references the Lot | Condo units, parking slots and house-and-lot packages modeled as lots; lot merge or split; price increases on unsold lots only; management / model-unit holds; VAT threshold treatment | Extend | Sales admin / Project Development
07.2 | 07 | Inventory & financing options setup | Financing options setup | New price list or promo scheme | Scheme (spot cash, deferred cash, bank, Pag-IBIG, IHF); reservation fee; DP % and months; discount %; interest rate; loanable %; term; validity | Payment-term templates → sales computation (09.1) → amortization engine (11) | Promo expiry; scheme change after reservation (restructuring); Pag-IBIG loan ceilings | Extend | Sales admin / Project Development
08.1 | 08 | Sales channel accreditation | Broker / agent accreditation | Application received | Firm and agent names; PRC license no. and expiry; DHSUD registration; TIN and COR 2303; bank details; commission tier; parent firm; validity | Contacts (partner tags) → Documents → Approvals → commission plan; selectable on CRM / sales order | Expired license must block tagging; agent changing firms mid-deal; split commission between firms | Configure | Sales admin
09.1 | 09 | Sales (reservation to contract to sell) | Sales computation & reservation | Buyer selects unit and scheme | Buyer name, TIN, IDs, civil status; co-borrower; unit; TCP; discounts; VAT; other charges; reservation fee; DP schedule; balance; scheme; broker / agent; promo code | CRM opportunity → sales quotation (computation) → invoice / receipt for reservation fee → unit status reserved | Double reservation of one unit (lock needed); bounced RF check; reservation expiry and RF forfeiture; discount above authority; OFW buyers with SPA | Extend | Sales / sales admin
09.2 | 09 | Sales (reservation to contract to sell) | CTS generation | Documents complete and DP policy met | CTS no.; parties; unit; TCP; payment schedule (due dates, principal / interest split); penalty clause; Maceda clause; signatories; notarization date | Sales order confirmed → Sign → Documents → buyer ledger and amortization schedule (11) | Amendments: transfer of rights, unit swap, restructuring; co-owner change; death of buyer | Extend | Sales / sales admin
09.3 | 09 | Sales (reservation to contract to sell) | Revenue recognition | CTS signed and collectability threshold met (per policy) | % completion; collections %; cost-to-complete; significant financing component | Periodic journal in Accounting driven by project % complete (06.1) and collections (11.2) | PFRS 15 over-time recognition assumptions; reversal on cancellation; auditor-agreed thresholds | Extend | Sales / sales admin
10.1 | 10 | Leasing | Lease contract & billing | Tenant accepts term sheet | Tenant; unit; lease rate; escalation %; term; start / end; security deposit; advance rent; CUSA; utilities; PDCs; VAT / EWT | Unit status leased → Rental or Subscription → recurring invoices → AR | Pre-termination; holdover; rent-free periods; applying deposit against damages | Configure | Leasing / sales
11.1 | 11 | Accounts monitoring (documentation, receipting, collection) | Buyer documentation | Reservation or CTS stage reached | Checklist per scheme; document status; received date; expiry (IDs); file | Documents workspace linked to buyer and unit; completeness gate for CTS (09.2) and takeout (13.1) | Expired documents; consularized documents from abroad | Configure | Credit & collection
11.2 | 11 | Accounts monitoring (documentation, receipting, collection) | Receipting & collection posting | Payment received | Payor; amount; mode (cash, check, PDC, transfer, online); check no., bank, date; allocation (RF, DP, amortization, penalty, other charges); invoice series; VAT breakdown | Accounting payment → allocation on buyer ledger; BIR-registered invoice series (CAS / e-invoicing) | PDC warehousing; bounced checks; partial or over-payment; unidentified deposits; EOPT invoice-vs-receipt rules | Extend | Credit & collection
11.3 | 11 | Accounts monitoring (documentation, receipting, collection) | SOA, delinquency & aging | Monthly cycle (timer) or due date lapsed | Amount due; paid; balance; days past due; penalty rate and amount; aging bucket | Follow-up reports → demand letters → collection dashboard → cancellation trigger (12.1) | Penalty waivers (approval); restructuring; grace periods under RA 6552 | Extend | Credit & collection
12.1 | 12 | Cancellations & return to inventory | Cancellation & refund | Buyer request, or default beyond grace | Reason code; total paid; years of installments; cash surrender value (50% + 5%/yr after 5 yrs, max 90%); deductions; notarial notice date; effective date; approval | Accounting reversal (AR, revenue, commission clawback) → AP refund (16) → unit status available | Under 2 years paid (no CSV, 60-day grace); disputes; refunds in installments; unit already turned over | Extend | Credit & collection / Legal
13.1 | 13 | Bank / Pag-IBIG takeout & in-house financing | Bank / Pag-IBIG takeout | Equity fully paid | Lender; loan amount; loanable %; requirements checklist; application date; LOG / NOA no. and date; release date; proceeds; deductions (fees, MRI); DOAS | Takeout tracker → Titling (annotation) → Accounting (proceeds applied) → buyer balance closed | Disapproval or partial approval (buyer pays gap); Pag-IBIG buyback guarantee; LOG expiry | Extend | Loans & financing
13.2 | 13 | Bank / Pag-IBIG takeout & in-house financing | In-house financing | IHF chosen and approved | Principal; rate; term; amortization method; due day; collateral | Amortization schedule → monthly SOA (11.3) → interest income | Repricing; early payoff; later refinancing to a bank | Extend | Loans & financing
14.1 | 14 | TORC – taxes and other related charges | TORC (taxes and other related charges) processing | Full payment reached / title transfer started | DST; transfer tax; registration fees; other fees; budget line; payee agency; liquidation; amount rechargeable to buyer | Titling → cash advance or bill → AP (16) → Accounting (buyer charge or project cost) | Zonal-value updates; unliquidated advances; surcharges | Configure | Titling
15.1 | 15 | Unit preparation & delivery | Turnover | Unit ready and account eligible | Unit; inspection date; punch-list items; rectification status; acceptance date; keys; meter readings; warranty end date | Field Service / Project tasks → Sign (acceptance) → unit status turned over → PM onboarding and dues (18.1) | Buyer no-show (deemed acceptance clause); major defects; turnover before full payment by exception | Configure | Customer care / turnover
16.1 | 16 | Accounts payable processing | AP invoice processing | Vendor bill received | Vendor; TIN; bill no. and date; PO ref; receipt / accomplishment ref; VAT; EWT ATC code; retention; due date; analytic distribution; approver | Purchase ↔ bill (3-way match) → Approvals → payment batch → bank → BIR 2307 → budget actuals | Bills without PO; duplicates; partial payment; supplier advances; foreign currency | Standard | Accounting – AP
16.2 | 16 | Accounts payable processing | Disbursement | Approved bill falls due | Payment method; bank; check no.; release date; 2307 | Accounting → bank file or check printing → bank reconciliation | Stale or cancelled checks; payment holds | Standard | Accounting – AP
17.1 | 17 | Commissions & sales incentives | Commission accrual & release | CTS signed (accrual); collection threshold reached (release) | Broker / agent; rate; base (net TCP); tranche %; release condition; EWT; non-cash incentives; clawback rule | Sales → commission computation → broker bill → AP (16); non-cash incentives via Purchase / Inventory | Clawback on cancellation; split deals; commission on discounted price; manager overrides | Extend | Sales admin
18.1 | 18 | Property management | Homeowner onboarding & dues | Turnover accepted | Homeowner; unit; dues rate; start date; billing cycle; utilities | Subscription / recurring invoices → collection → HOA fund accounting | Dues arrears blocking services; developer-paid dues on unsold units | Configure | Property management
18.2 | 18 | Property management | Servicing & PM expenses | Service request or scheduled maintenance | Ticket; category; unit; SLA; warranty flag; cost; vendor | Helpdesk / Field Service → Purchase → AP (property-management expenses) | Warranty vs chargeable; emergency repairs | Configure | Property management
18.3 | 18 | Property management | HOA turnover | Turnover criteria met | HOA registration; fund balance; assets; documents | Final PM accounting close → Documents | Disputes on fund balance or common areas | Configure | Property management
19.1 | 19 | Title delivery | Title processing & delivery | Full payment, or lender requires title for release | DOAS date; eCAR no.; new TCT / CCT no.; tax declaration; release date; recipient (buyer or lender) | Title tracker → Documents → buyer notice; feeds takeout release (13.1) | Mother title not yet subdivided; lost documents; unpaid real-property tax | Extend | Titling
X1.1 | X1 | Forecasts | Rolling forecasts | Month-end close | Sales forecast; collection forecast; cost-to-complete; cash forecast | All modules → Spreadsheet / dashboards | Unapproved reservations inflating pipeline; stale construction progress | Configure | Finance – FP&A
X2.1 | X2 | KPIs & variance reports | KPIs & variance reporting | Period close | Budget vs actual by analytic account; absorption and sales velocity; collection efficiency; aging / DSO; % completion; cost variance | Accounting budget report → dashboards / BI | Timing differences (commitments vs actuals); reclassifications after close | Configure | Finance – FP&A

## Master Data
Object | Owning process | Key fields | Indicative Odoo home | Used by processes
Company / entity | 01 | Legal name, TIN, BIR registration, CAS permit, fiscal year | res.company | All
Analytic plans | 01 | Business unit, project, phase, cost center, expense type | Accounting › Analytic plans | 01, 03, 06, 16, X2
Budget line | 01 | Version, account, analytic, period, amount, status | Accounting › Budgets | 03, 06, 14, 16, X2
Land parcel | 04 | OCT/TCT, area, owner, cost, status, linked project | Custom land register | 04, 05, 19
Project / phase | 05 | Code, type, phases, blocks/towers, WBS, permits, LTS | project.project + analytic account | 06, 07, 09, X1
Lot (unit master) | 07 | Lot ID, project / phase / block, house model, lot and floor area, price, construction status, sales status, title no., current buyer / CTS | Lot master model (vendor-proposed), linked to product.product and project analytic | 09–15, 18, 19
Payment scheme | 07 | Scheme type, RF, DP %/months, rate, term, validity | Payment terms + custom scheme | 09, 11, 13
Buyer / co-borrower | 09 | Name, TIN, IDs, civil status, address, employer, SPA | res.partner | 09–15, 18, 19
Broker / agent | 08 | PRC license, DHSUD reg., TIN, tier, validity, parent firm | res.partner (tagged) | 09, 17
Contract to sell | 09 | CTS no., unit, TCP, schedule, clauses, signatures | sale.order + sign.request | 11, 12, 13, 17
Buyer ledger / schedule | 11 | Due lines, allocations, penalties, balance | account.move / account.payment + custom schedule | 11, 12, 13, X1
Vendor / contractor | 03 | TIN, VAT status, ATC codes, bank, accreditation | res.partner | 03, 06, 14, 16, 18
Title record | 19 | Mother / derivative title, eCAR, tax dec, custody, release | Custom title tracker + documents.document | 04, 13, 19
Service ticket | 18 | Unit, category, SLA, warranty flag, cost | helpdesk.ticket | 15, 18

## Lot Touchpoints
Process | What it does to the Lot (vendor-proposed master model) | Fields needed on Lot | Vendor response
04 Land acquisition · 05 Project setup | Mother title and project / phase / block give the Lot its parent references
06 Construction | Updates construction status and % completion
07 Inventory | Creates the Lot, prices it, sets sales status to available
09 Sales · 12 Cancellations | Reserved → sold; cancelled → available again (return inventory)
11 Accounts monitoring · 13 Takeout | Buyer ledger, schedule and loan status hang off the Lot's active CTS
15 Turnover · 18 Property management | Turned-over flag, warranty dates, homeowner and dues
19 Title delivery | Derivative title number, custody and release

## Open Items
# | Item | Owner | Decision | Target date | Status
Q1 | TORC scope. TORC = taxes and other related charges. List each tax and charge PHI books under it, who shoulders each (buyer vs developer), and whether it is advanced and recharged or billed upfront. |  |  |  | Open
Q2 | Process numbering. Confirm the proposed numbers for 01–03, 05–13 and 17 so every BRD chapter uses one ID set. |  |  |  | Open
Q3 | Turnover eligibility. Which payment status allows turnover (equity paid, loan approved, fully paid) and who can approve exceptions? |  |  |  | Open
Q4 | Revenue recognition. Agree the PFRS 15 method, collectability threshold and POC source with the external auditor before the Accounting design. |  |  |  | Open
Q5 | Commission release rules. Tranches, clawback on cancellation, and treatment of in-house vs external brokers. |  |  |  | Open
Q6 | Invoicing compliance. Current BIR CAS permit status and e-invoicing timeline — decides whether Odoo prints the official invoice series from go-live. |  |  |  | Open
Q7 | Lot as master model (vendor proposal). Confirm whether "Lot" is a custom real-estate model or Odoo's serial/lot record (stock.lot), and how it represents condo units, parking slots, house-and-lot packages, and merged or split lots. |  |  |  | Open
Q8 | Lot status design. Separate construction status and sales status fields on the Lot, and who may change each (Construction, Sales admin, Credit & collection, Titling). |  |  |  | Open
Q9 | Migration from In4 Velocity. How much buyer-ledger history moves (open balances only, or full payment history needed for Maceda computations)? |  |  |  | Open
Q10 | Approval matrix (DOA). Amount thresholds per document type, per company and per project to configure in Approvals. |  |  |  | Open

## SOW Gap Analysis
Gap analysis — blueprint (SIPOC + data matrix) vs vendor SOW
Rating: Covered = SOW clearly delivers it · Partial = some of it, gaps listed · Not covered = absent. Yellow columns are for PHI and vendor responses.
Summary
Covered | 8
Partial | 12
Not covered | 1
High-priority gaps (processes) | 8
Processes assessed | 21
Deferred to next phase | 2
Proc ID | Process | Blueprint requirement | Coverage rating | SOW coverage (section / item) | Gaps and missing scope | Priority | Recommended action | Matrix steps affected | SOW items mapped | Dev-days touching process* | PHI owner response | Vendor response | Status
01 | Budget setup (corporate & project) | Corporate + life-of-project budgets by phase and cost code; budget cycle (prepare → consolidate → ManCom approval → lock); budget check on PR/PO/bill; realignment | Partial | §3.1 G Finance Core (corporate & department budget, burn-rate; TORC budget rule builder; project P&L; budget vs actual) | No budget preparation / consolidation / approval workflow or versioning; no multi-year project budget or re-baseline; budget check at PR/PO stage not stated (only TORC dispensing). | High | Clarify in BRD: budget cycle workflow, versions, PR/PO budget check. Price as CR if not in base. | 01.1, 01.2, 01.3 | 0 | 0 |  |  | Open
02 | Corporate & project financing | Loan drawdown, allocation to projects, interest accrual and capitalization, debt service | Partial | §3.3 #99–100 Company Loans (payment processing, schedule view, cash-flow forecast link) | Debt service covered. Drawdown allocation per project, interest capitalization to project cost (and stop at completion), covenant tracking not mentioned. | Medium | Add allocation + capitalized-interest rules to BRD; confirm with Finance. | 02.1 | 2 | 12.96 |  |  | Open
03 | Corporate expenses | Request → budget check → PO/contract → receipt → bill → AP for corporate spend | Covered | §3.1 F Non-project payments (same approval & posting pipeline); §3.2 Purchase, Accounting | Petty cash / reimbursements (Odoo Expenses) not mentioned. | Low | Confirm Expenses app is in scope or handled manually. | 03.1 | 0 | 0 |  |  | Open
04 | Land acquisition | Due diligence, agreements, milestone payments, taxes and title transfer, land bank | Covered | §3.1 C Land Acquisition; D Land banking register & carrying costs; §3.3 #1–4, 12, 16–26, 29–30, 56–63, 86–87 | Strong coverage (multi-owner, DOAS, BIR/LGU filing tracker, land bank). JV with landowner paid in units (non-cash allocation) not mentioned; CARP/heirs flags depend on DD checklist content. | Medium | Confirm JV / land-for-units treatment in Discovery. | 04.1, 04.2, 04.3 | 30 | 171.36 |  |  | Open
05 | Project setup & project financing | Project master, phases/WBS, analytic account, permits (DP, ECC, BP, CR/LTS); block selling without LTS | Partial | §3.1 C Project Setup Wizard, launch readiness gate; D Land bank → project conversion; §3.3 #6–15, 37, 62, 70 | No explicit permit / License to Sell tracker; 5-criteria launch gate is land-oriented (title, payments, construction) — LTS not listed as a criterion. Wizard Step 1 (Info) is in §3.1 but not itemized in §3.3. | High | Add LTS / DHSUD permits as a launch-gate criterion and permit register. Ask why Step 1 is unpriced. | 05.1 | 15 | 77.76 |  |  | Open
06 | Project expenses & construction (milestone-based) | Contract award, progress billing with retention and DP recoupment, variation orders, % completion, POC link | Partial | §3.1 B Subcontractor billing workflow; F Contracts & deliverables (milestones, retention); D construction schedule, cost ledger; §3.3 #66–69 | Retention and milestone release covered. DP recoupment, variation orders, liquidated damages, back-charges not mentioned. BOQ listed in §3.2 but no build item. % completion does not feed revenue recognition (see C1). | High | Walk vendor through 06.1 exceptions; get written coverage or CR price. | 06.1 | 6 | 31.68 |  |  | Open
07 | Inventory & financing options setup | Lot as unit master, pricing and escalation, construction + sales status, financing schemes and payment terms | Covered | §3.1 D Inventory (Lot master, pricing floor, governed status workflow); H pricing rules engine; §3.3 #5, 16, 27–28, 69, 73 | Lot model (lam.lot) is built around block/lot land parcels. Condo units (tower-floor-unit), parking slots and house-and-lot packages not addressed. Pag-IBIG not listed among pricing schemes in H (only in Customer Loans). | High | Confirm the Lot model handles vertical projects before sign-off. | 07.1, 07.2 | 7 | 36 |  |  | Open
08 | Sales channel accreditation | Broker/agent accreditation, PRC/DHSUD/TIN docs, validity, commission scheme | Covered | §3.1 E Partner & accreditation; §3.3 #40, 48–49, 55, 64 | Expiry alerts included. Agent moving firms mid-deal not explicit. | Low | Confirm in BRD. | 08.1 | 5 | 24.48 |  |  | Open
09 | Sales (reservation to contract to sell) | Sales computation, reservation, document & credit check, CTS generation and notarization, payment schedule, revenue recognition | Partial | §3.1 H Reservation; E Sales; A buyer docs (OCR); §3.3 #31–39, 50–52, 54 | Reservation → SO flow is strong. No Contract to Sell (CTS) document template, signing and notarization tracking — the SO stands in for the contract. No credit-evaluation step. Discount approval implied, not explicit. | High | Add CTS generation (template, e-sign/notarization status) and credit check to scope. | 09.1, 09.2, 09.3 | 15 | 92.16 |  |  | Open
10 | Leasing | Lease term sheet, contract, recurring rent/CUSA billing, deposits, renewals | Not covered | None | Leasing is absent from the SOW. | Medium | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | 10.1 | 0 | 0 |  |  | Deferred (next phase)
11 | Accounts monitoring (documentation, receipting, collection) | Buyer documents, BIR-compliant receipting, collection posting and allocation, SOA, penalties, aging, demand letters | Partial | §3.1 I Customer Loans (allocation, statements, aging); J Customer Servicing (SOA); §3.3 #34, 39, 74–77, 95, 97–98 | Allocation (penalty → interest → principal), SOA, grace period and aging covered. PDC warehousing and bounced checks, demand-letter generation and BIR-registered invoice/receipt series not mentioned. | High | Add PDC management and demand letters; confirm BIR invoice series (see C2). | 11.1, 11.2, 11.3 | 15 | 86.4 |  |  | Open
12 | Cancellations & return to inventory | Maceda-compliant cancellation: grace, notarial notice, cash surrender value, refund/forfeiture, reversals, return to inventory | Partial | §3.3 #36 (SO cancel releases lot), #43 (commission clawback), H reservation cancel/release | Only the inventory release and commission clawback are covered. No RA 6552 cash-surrender-value computation, notice tracking, refund processing, forfeiture income or AR/revenue reversal. | High | Add a cancellation workflow with Maceda calculator as base scope, not CR — it is a statutory requirement. | 12.1 | 1 | 7.2 |  |  | Open
13 | Bank / Pag-IBIG takeout & in-house financing | Bank/Pag-IBIG takeout tracking (requirements, LOG/NOA, release, proceeds) and in-house financing | Partial | §3.1 I Customer Loans & Financing; B turnover aging uses takeout status; §3.3 #39, 96–98 | IHF is well covered (amortization, restructuring, compounding). Takeout workflow — requirements checklist, submission, LOG/NOA, title annotation, proceeds release, Pag-IBIG buyback — is only implied via a takeout status. | High | Specify takeout tracker fields and stages in BRD. | 13.1, 13.2 | 4 | 28.8 |  |  | Open
14 | TORC – taxes and other related charges | TORC = taxes and other related charges on title transfer: compute, fund, pay agencies, liquidate, recharge to buyer | Partial | §3.1 F Project payments (TORC): budget vs actual per project/lot; G TORC budget rule builder & dispensing engine | The SOW treats TORC as a project budget-dispensing mechanism. Buyer-side taxes and charges, recharge to buyer ledger and liquidation of cash advances are not described. Definitions may not match. | High | Align the TORC definition with the vendor in writing before BRD. | 14.1 | 0 | 0 |  |  | Open
15 | Unit preparation & delivery | Buyer turnover eligibility, joint inspection, punch list, acceptance, keys, warranty | Covered | §3.1 B turnover aging; §3.3 #72, 79, 85 (turnover & dual signatures, portal move-in status, defect tickets) | Warranty period tracking not mentioned. Note: 'Turnover' in §3.3 #70–73 means the internal land → sales hand-off, not buyer turnover. | Medium | Keep the two meanings of 'turnover' separate in the BRD glossary. | 15.1 | 7 | 41.76 |  |  | Open
16 | Accounts payable processing | Invoice capture, 3-way match, approval (DOA), EWT, payment, BIR 2307 | Covered | §3.1 F Supplier & payments (approval matrix, roll-up, retention, T-7 alerts); §3.3 #45, 59–60 | EWT named in objectives; BIR 2307 / SAWT / QAP / alphalist outputs not listed explicitly. | Medium | Confirm PH localization outputs (see C2). | 16.1, 16.2 | 4 | 27.36 |  |  | Open
17 | Commissions & sales incentives | Commission accrual, tranche release, splits, EWT, clawback, non-cash incentives | Covered | §3.1 A, E compensation engine & payout; §3.3 #41–47, 53, 91 | Well covered, including vesting, clawback and disputes. | Low | None. | 17.1 | 9 | 61.92 |  |  | Open
18 | Property management | Homeowner onboarding, dues billing and collection, servicing, PM expenses, HOA turnover | Partial | §3.3 #81–84 Helpdesk (servicing only) | Only servicing tickets are covered. Association dues billing/collection, HOA fund accounting and HOA turnover are absent. | Medium | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | 18.1, 18.2, 18.3 | 4 | 24.48 |  |  | Deferred (next phase)
19 | Title delivery | Buyer title transfer: DOAS, taxes/fees, eCAR, new TCT/CCT, release to buyer or bank | Partial | §3.1 A title status integration (Pre-BIR → Title Release); §3.3 #29 Title tab, #78 portal documents | Status visibility is covered. The processing workflow (documents, fee payment, eCAR, RD transfer, release to lender) is not itemized — the BIR/LGU filing tracker (#26) is for land acquisition. | Medium | Extend #26 filing tracker to buyer title transfer. | 19.1 | 2 | 10.08 |  |  | Open
X1 | Forecasts | Rolling sales, collection, cost-to-complete and cash forecasts | Partial | §3.1 G company performance report (cash-flow projections); §3.3 #100 cash-flow forecast link | Cash-flow projection mentioned. Sales and collection forecasts and cost-to-complete not described. | Low | Define forecast outputs in BRD. | X1.1 | 1 | 4.32 |  |  | Open
X2 | KPIs & variance reports | Budget vs actual and KPI reporting across processes | Covered | §3.1 G Finance BI; many dashboards (§3.3 #1–6, 86–91) | Well covered. | Low | None. | X2.1 | 7 | 38.88 |  |  | Open
* Items that touch several processes are counted in each, so this column does not sum to the SOW total.
Cross-cutting gaps
Ref | Topic | SOW reference | Coverage rating | Gap | Recommended action | Priority | PHI owner response | Vendor response | Status
C1 | Revenue recognition (PFRS 15, over-time / % of completion) | Not in SOW | Not covered | No mention of revenue recognition, POC journals or significant financing component — central to a developer's financials. | Add to Finance Core; agree method with external auditor first. | High |  |  | Open
C2 | BIR compliance detail | Objectives mention EWT and BIR; §9 excludes non-PH filings | Partial | CAS permit / registered invoice series, EOPT invoicing rules, e-invoicing (EIS), 2307, SAWT, QAP, alphalist and VAT on real property thresholds are not itemized. | Get a written list of PH statutory outputs delivered. | High |  |  | Open
C3 | Data migration from In4 Velocity | §3.4 data migration; §7 CSV Rule; §9 excludes history beyond cut-off | Partial | Only templated master data and opening balances. Maceda computations need full payment history (years paid); commission and takeout status also need history. | Agree cut-off and which buyer-ledger history migrates; size it now, not as flex. | High |  |  | Open
C4 | Vertical / condo projects in the Lot model | §3.1 D, §8 (existing Lot model 'stable and documented') | Partial | Lot model is land-lot based (block/lot, TCT). CCT titles, tower-floor-unit, parking not addressed. | Confirm project mix and model design. | High |  |  | Open
C5 | Existing internal systems | §9 limits integrations to CSV/MT940 imports | Not covered | No data feed to PHI's existing internal systems (e.g., BI dashboards, SharePoint document stores). | List systems that must read Odoo data; decide API vs export. | Medium |  |  | Open
C6 | Mockups referenced but not attached | §3.3 'based on the Mockups' | Partial | Scope items are defined by mockups that are not part of the SOW; items #62–64 have no description at all. | Attach mockups as an SOW annex; describe #62–64. | Medium |  |  | Open
In the SOW but not yet in the blueprint (update the blueprint)
# | SOW capability | Blueprint process(es) | Suggested blueprint update
S1 | Buyer self-service portal (SOA, payments, documents, concerns, turnover status) | 11, 15, 19 | Add portal as a channel in SIPOC for 11 and 15
S2 | Broker / agent portal (listings, lead registration, reservation requests, commission view) | 08, 09, 17 | Add as a channel in 08 and 09
S3 | Supplier accreditation workflow and performance rating | 03, 06, 16 | Add supplier accreditation as a step in procure-to-pay
S4 | Land banking register, carrying cost ledger and conversion to project | 04, 05 | Add land bank to 04 outputs and 05 inputs
S5 | 5-criteria launch readiness gate and internal land → sales turnover | 05, 07 | Add gate to diagram B before lot creation
S6 | Helpdesk with SLA, CSAT and construction punch-list | 15, 18 | Add CSAT and SLA to 15 / 18 outputs
S7 | Company loan payment processing | 02 | Already in 02 — confirm scope depth
S8 | Document OCR for buyer IDs and proof of income | 09, 11 | Add to 11.1 hand-off

## SOW Scope Map
SOW §3.3 customizations mapped to blueprint processes
Source: Achieve Without Borders SOW S343096 (Odoo v19), dated 24 Sep 2026. Dev man-days transcribed as stated in the SOW.
# | Section | Feature | Dev man-days | Blueprint process(es) | Process name(s)
1 | Dashboard | Acquisition KPI Cards | 4.32 | 04 | Land acquisition
2 | Dashboard | Attention Required List | 5.76 | 04 | Land acquisition
3 | Dashboard | Project Progress Bars | 2.88 | 04 | Land acquisition
4 | Dashboard | Quick Navigation | 2.88 | 04 | Land acquisition
5 | Dashboard | Lot Inventory | 5.76 | 07 | Inventory & financing options setup
6 | Dashboard | Project | 4.32 | 05 | Project setup & project financing
7 | Projects & Pipeline | Project Consolidated View | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
8 | Projects & Pipeline | Project Search & Filters | 4.32 | 05 | Project setup & project financing
9 | Project Setup Wizard | Step 2 - Site Details | 4.32 | 05 | Project setup & project financing
10 | Project Setup Wizard | Step 3 - Targets | 4.32 | 05 | Project setup & project financing
11 | Project Setup Wizard | Step 4 - Team Assignment | 4.32 | 05 | Project setup & project financing
12 | Project Setup Wizard | Step 5 - Milestone Template | 5.76 | 04 | Land acquisition
13 | Project Setup Wizard | Step 6 - Documents | 4.32 | 05 | Project setup & project financing
14 | Project Setup Wizard | Step 7 - Review & Launch | 4.32 | 05 | Project setup & project financing
15 | Project Setup Wizard | Sample Form Previews | 4.32 | 05 | Project setup & project financing
16 | Lot Onboarding Form | Lot Master Data | 5.76 | 04, 07 | Land acquisition; Inventory & financing options setup
17 | Lot Onboarding Form | Pricing & Source | 4.32 | 04 | Land acquisition
18 | Lot Onboarding Form | Seller/Owner Details | 4.32 | 04 | Land acquisition
19 | Lot Onboarding Form | Attachments Checklist | 4.32 | 04 | Land acquisition
20 | Lot Onboarding Form | Auto Due-Diligence Checklist | 7.2 | 04 | Land acquisition
21 | Lot Onboarding Form | Approval Route | 5.76 | 04 | Land acquisition
22 | Lot Onboarding Form | Bulk Lot Onboarding Wizard | 7.2 | 04 | Land acquisition
23 | Acquisition & Payments (Multi-Owner) | Multi-Owner Land Sources | 8.64 | 04 | Land acquisition
24 | Acquisition & Payments (Multi-Owner) | Per-Owner Milestone Schedule | 8.64 | 04 | Land acquisition
25 | Acquisition & Payments (Multi-Owner) | Auto-Drafted Deed of Absolute Sale | 8.64 | 04 | Land acquisition
26 | Acquisition & Payments (Multi-Owner) | BIR / LGU Filing Tracker | 7.2 | 04 | Land acquisition
27 | Lot Detail & Lifecycle | Lot Lock / Reusable Pill | 4.32 | 07, 09 | Inventory & financing options setup; Sales (reservation to contract to sell)
28 | Lot Detail & Lifecycle | Locked Ribbon & Kanban Lock Icons | 4.32 | 07 | Inventory & financing options setup
29 | Lot Detail & Lifecycle | Title Tab | 5.76 | 04, 19 | Land acquisition; Title delivery
30 | Lot Detail & Lifecycle | DD / Milestones / Construction Tabs | 7.2 | 04, 06 | Land acquisition; Project expenses & construction (milestone-based)
31 | CRM → Reservation → Sales Order | Lot Interest & Availability Browser | 7.2 | 09 | Sales (reservation to contract to sell)
32 | CRM → Reservation → Sales Order | Reserve Lot from Opportunity | 7.2 | 09 | Sales (reservation to contract to sell)
33 | CRM → Reservation → Sales Order | Soft-Hold with Expiry (Reservation) | 7.2 | 09 | Sales (reservation to contract to sell)
34 | CRM → Reservation → Sales Order | Reservation Fee Payment & Receipt | 7.2 | 09, 11 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection)
35 | CRM → Reservation → Sales Order | Opportunity Won → Auto-Create Sales Order | 7.2 | 09 | Sales (reservation to contract to sell)
36 | CRM → Reservation → Sales Order | SO Confirm / Lot Lock Flow | 7.2 | 09, 12 | Sales (reservation to contract to sell); Cancellations & return to inventory
37 | CRM → Reservation → Sales Order | Launch-Readiness Gate on SO Confirm | 5.76 | 05, 09 | Project setup & project financing; Sales (reservation to contract to sell)
38 | CRM → Reservation → Sales Order | Double-Sell / Double-Reserve Constraint | 5.76 | 09 | Sales (reservation to contract to sell)
39 | CRM → Reservation → Sales Order | Customer Payment Schedule Generator | 8.64 | 09, 11, 13 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
40 | Broker Commission | Broker / Agent Master Record | 4.32 | 08 | Sales channel accreditation
41 | Broker Commission | Commission Plan Setup | 8.64 | 17 | Commissions & sales incentives
42 | Broker Commission | Commission Tagging on Reservation / SO | 4.32 | 17 | Commissions & sales incentives
43 | Broker Commission | Commission Computation Engine | 11.52 | 17 | Commissions & sales incentives
44 | Broker Commission | Commission Release / Vesting Rules | 7.2 | 17 | Commissions & sales incentives
45 | Broker Commission | Commission Voucher & Payout | 7.2 | 16, 17 | Accounts payable processing; Commissions & sales incentives
46 | Broker Commission | Broker Commission Statement | 5.76 | 17 | Commissions & sales incentives
47 | Broker Commission | Commission Audit & Disputes | 5.76 | 17 | Commissions & sales incentives
48 | Broker Portal | Broker Portal Login & Access | 4.32 | 08 | Sales channel accreditation
49 | Broker Portal | My Listings & Lot Availability | 5.76 | 07, 08 | Inventory & financing options setup; Sales channel accreditation
50 | Broker Portal | Register Lead / Buyer Referral | 5.76 | 09 | Sales (reservation to contract to sell)
51 | Broker Portal | Reservation Request via Portal | 7.2 | 09 | Sales (reservation to contract to sell)
52 | Broker Portal | Deal Status Tracker | 4.32 | 09 | Sales (reservation to contract to sell)
53 | Broker Portal | Commission Visibility | 5.76 | 17 | Commissions & sales incentives
54 | Broker Portal | Document Upload | 4.32 | 09, 11 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection)
55 | Broker Portal | Portal Notifications | 4.32 | 08 | Sales channel accreditation
56 | Payment Milestones & Reminders | Milestone Templates | 4.32 | 04 | Land acquisition
57 | Payment Milestones & Reminders | Lot Milestones | 5.76 | 04 | Land acquisition
58 | Payment Milestones & Reminders | Automated Payment Reminders | 7.2 | 04, 11 | Land acquisition; Accounts monitoring (documentation, receipting, collection)
59 | Payment Milestones & Reminders | Invoice Generation from Milestones | 5.76 | 04, 16 | Land acquisition; Accounts payable processing
60 | Approvals & Documents | Milestone Release Approvals | 5.76 | 04, 16 | Land acquisition; Accounts payable processing
61 | Approvals & Documents | Central Document Repository | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
62 | Approvals & Documents | Project Approval Workflow | 5.76 | 05 | Project setup & project financing
63 | Approvals & Documents | Lot Approval Workflow | 5.76 | 04 | Land acquisition
64 | Approvals & Documents | Broker Approval Workflow | 5.76 | 08 | Sales channel accreditation
65 | Approvals & Documents | Audit Logs | 4.32 | X2 | KPIs & variance reports
66 | Construction Monitoring | Progress Photo Gallery | 5.76 | 06 | Project expenses & construction (milestone-based)
67 | Construction Monitoring | Cluster Health Board | 7.2 | 06 | Project expenses & construction (milestone-based)
68 | Construction Monitoring | Cluster Alert Cron | 4.32 | 06 | Project expenses & construction (milestone-based)
69 | Construction Monitoring | Construction % to Stage | 4.32 | 06, 07 | Project expenses & construction (milestone-based); Inventory & financing options setup
70 | Launch Readiness & Turnover | 5-Criteria Launch Readiness Gate | 7.2 | 05 | Project setup & project financing
71 | Launch Readiness & Turnover | Pre-Turnover Inspection Checklist | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
72 | Launch Readiness & Turnover | Turnover Inspection & Dual Signatures | 7.2 | 05, 15 | Project setup & project financing; Unit preparation & delivery
73 | Launch Readiness & Turnover | CRM / Saleable Unit Hand-off | 5.76 | 07 | Inventory & financing options setup
74 | Customer Portal | My Lots & Purchase Summary | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
75 | Customer Portal | Payment Schedule & Balance | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
76 | Customer Portal | Online Payment / Payment Submission | 8.64 | 11 | Accounts monitoring (documentation, receipting, collection)
77 | Customer Portal | Payment Reminders & Receipts | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
78 | Customer Portal | Document Access | 4.32 | 11, 19 | Accounts monitoring (documentation, receipting, collection); Title delivery
79 | Customer Portal | Turnover & Move-In Status | 4.32 | 15 | Unit preparation & delivery
80 | Customer Portal | Profile & Contact Management | 4.32 | 11 | Accounts monitoring (documentation, receipting, collection)
81 | Helpdesk | Ticket Intake Channels | 5.76 | 15, 18 | Unit preparation & delivery; Property management
82 | Helpdesk | Ticket Categories & SLA | 5.76 | 15, 18 | Unit preparation & delivery; Property management
83 | Helpdesk | Ticket Assignment & Routing | 5.76 | 15, 18 | Unit preparation & delivery; Property management
84 | Helpdesk | Ticket Workbench | 7.2 | 15, 18 | Unit preparation & delivery; Property management
85 | Helpdesk | Defect / Punch-List Tickets | 5.76 | 15 | Unit preparation & delivery
86 | Reporting & BI | Cost vs Paid Analysis | 5.76 | 04, X2 | Land acquisition; KPIs & variance reports
87 | Reporting & BI | Milestone Aging Report | 4.32 | 04, X2 | Land acquisition; KPIs & variance reports
88 | Reporting & BI | Summary Reports (PDF/XLSX) | 7.2 | X2 | KPIs & variance reports
89 | Reporting & BI | Audit / Status Reports | 5.76 | X2 | KPIs & variance reports
90 | Reporting & BI | Customer (BI and Report) | 5.76 | 11, X2 | Accounts monitoring (documentation, receipting, collection); KPIs & variance reports
91 | Reporting & BI | Broker (BI and Report) | 5.76 | 17, X2 | Commissions & sales incentives; KPIs & variance reports
92 | Configuration & Settings | Reminder Offsets | 2.88 | 04, 11 | Land acquisition; Accounts monitoring (documentation, receipting, collection)
93 | Configuration & Settings | Cluster Thresholds | 2.88 | 06 | Project expenses & construction (milestone-based)
94 | Configuration & Settings | SO Gating Toggle | 2.88 | 09 | Sales (reservation to contract to sell)
95 | Configuration & Settings | Grace Period | 2.88 | 11 | Accounts monitoring (documentation, receipting, collection)
96 | Customer Loans | Customer Loan Configuration | 7.2 | 13 | Bank / Pag-IBIG takeout & in-house financing
97 | Customer Loans | Automated Customer Loan Payment Processing | 8.64 | 11, 13 | Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
98 | Customer Loans | Customer Payment Schedule List View | 4.32 | 11, 13 | Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
99 | Company Loans | Automated Company Loan Payment Processing | 8.64 | 02, 16 | Corporate & project financing; Accounts payable processing
100 | Company Loans | Company Loan Schedule List View | 4.32 | 02, X1 | Corporate & project financing; Forecasts
Total itemized dev man-days |  |  | 573.12
Section subtotal check
| Section | SOW stated subtotal | Computed from items | Difference
| Dashboard | 25.92 | 25.92 | 0
| Projects & Pipeline | 10.08 | 10.08 | 0
| Project Setup Wizard | 31.68 | 31.68 | 0
| Lot Onboarding Form | 38.88 | 38.88 | 0
| Acquisition & Payments (Multi-Owner) | 33.12 | 33.12 | 0
| Lot Detail & Lifecycle | 21.6 | 21.6 | 0
| CRM → Reservation → Sales Order | 63.36 | 63.36 | 0
| Broker Commission | 54.72 | 54.72 | 0
| Broker Portal | 41.76 | 41.76 | 0
| Payment Milestones & Reminders | 23.04 | 23.04 | 0
| Approvals & Documents | 33.12 | 33.12 | 0
| Construction Monitoring | 21.6 | 21.6 | 0
| Launch Readiness & Turnover | 25.92 | 25.92 | 0
| Customer Portal | 38.88 | 38.88 | 0
| Helpdesk | 30.24 | 30.24 | 0
| Reporting & BI | 34.56 | 34.56 | 0
| Configuration & Settings | 11.52 | 11.52 | 0
| Customer Loans | 20.16 | 20.16 | 0
| Company Loans | 12.96 | 12.96 | 0
| Total | 573.12 | 573.12 | 0
Blue = figures typed from the SOW. Differences of 0.00 mean the SOW section subtotals add up.

## SOW Effort Check
SOW §5.1 effort table — arithmetic and capacity check
Figures typed from §5.1 in blue. As printed, the Dev Lead column carries more days than Developer; ask the vendor to confirm.
Workstream | Lead Functional Consultant | BA | Dev Lead | Developer | QA | Infra | SOW stated total | Computed total | Difference
CRM, Buyer & Agent Portal | 10 | 7 | 29 | 10 |  |  | 56 | 56 | 0
Construction Monitoring | 6 | 5 | 19 | 6 |  |  | 36 | 36 | 0
Land Acquisition | 10 | 7 | 31 | 10 |  |  | 58 | 58 | 0
Inventory Management | 10 | 7 | 31 | 10 |  |  | 58 | 58 | 0
Sales Management & Commissions | 10 | 7 | 29 | 10 |  |  | 56 | 56 | 0
Supplier & Payments | 8 | 6 | 27 | 8 |  |  | 49 | 49 | 0
Finance Core & TORC Budget | 10 | 7 | 26 | 10 |  |  | 53 | 53 | 0
Reservation Management | 7 | 6 | 22 | 7 |  |  | 42 | 42 | 0
Customer Loans & Financing | 7 | 12 | 37 | 10 | 7 |  | 72 | 73 | 1
Customer Servicing Portal | 6 | 5 | 17 | 6 |  |  | 34 | 34 | 0
Data Migration, UAT & Training | 12 | 5 | 14 | 14 | 10 |  | 55 | 55 | 0
Infrastructure, Environments & Cutover |  |  | 3 |  |  | 29 | 32 | 32 | 0
Project Management & Governance | 48 | [5 empty] | 48 | 48 | 0
Hypercare (90 days post go-live) | [6 empty] | 90 | 90 | n/a (not split by role)
Total | 144 | 74 | 285 | 101 | 17 | 29 | 739 | 740 | 1
Capacity vs itemized build
Development capacity in §5.1 (Dev Lead + Developer) | 386
Itemized §3.3 customization dev man-days | 573.12
Shortfall (itemized minus capacity) | 187.12
Shortfall as % of itemized | 32.65%
§3.1 lists further features that have no §3.3 line (land banking, supplier module, TORC budget, project P&L), so the real gap is larger than shown.

## SOW Observations
Commercial and contract observations on the SOW
For discussion with the vendor and PHI Legal before signature. Not legal advice.
# | Observation | SOW reference | Finding | Impact on PHI | Suggested ask | Owner | Status
O1 | Build effort vs itemized scope | §3.3 vs §5.1 | The 100 itemized customizations total 573.12 dev-days. The two development columns in §5.1 (Dev Lead + Developer) total only 386 person-days, and §3.1 adds features not in §3.3 (land banking, supplier module, TORC budget, project P&L). | Scope looks under-resourced by roughly a third; risk of rushed build or later change orders. | Ask the vendor to reconcile, and confirm in writing that every §3.1 and §3.3 item is inside the Fixed Base Fee. |  | Open
O2 | §5.1 columns look swapped | §5.1 | As printed, Dev Lead carries 285 days and Developer 101 — the reverse of what a normal team shape would be. | Unclear team composition. | Ask for the corrected table and named roles. |  | Open
O3 | Arithmetic error: Customer Loans row | §5.1 | 7 + 12 + 37 + 10 + 7 = 73, but the row total says 72. The grand total of 739 uses 72. | Minor, but signals the table wasn't checked. | Ask for a corrected table. |  | Open
O4 | Payment gateway: in scope and out of scope | §3.3 #76 vs §9 | Item #76 (8.64 dev-days) builds online payment via gateway, while §9 lists payment gateway integration as out of scope. | PHI may pay for #76 and again for a CR. | Resolve: either remove #76's gateway part from the fee or remove it from §9. |  | Open
O5 | Two man-day rates | Cover page vs §10.2 | Base effort priced at PHP 10,000/day (739 × 10,000 = 7.39M); flex, overages and replenishments at PHP 12,000/day. | Gaps found in this analysis would be priced at the higher rate. | Negotiate the gap items into base scope before signing, or lock CRs at 10,000. |  | Open
O6 | Front-loaded billing | §11 | 50% (PHP 3.695M) is billed by BRD sign-off, before any build; 80% before go-live. | Reduced leverage if build quality slips. | Consider moving part of milestone 1 to SIT completion. |  | Open
O7 | Deemed acceptance | §11, §12 | Deliverables are accepted after 5 working days without written objection, and joining a later phase accepts the earlier one. | Short review window across 10 workstreams. | Extend to 10 working days, or name reviewers per deliverable in the RACI. |  | Open
O8 | Flex allocation is small | §10.3 | 35 person-days total; only 10 for change orders (PHP 120,000 at 12,000). | The High-priority gaps here will exceed it quickly. | Size the gaps now and add them to base scope. |  | Open
O9 | Lot model ownership | §8 | Assumes 'the existing custom Lot model' is stable and documented — suggests a vendor-owned pre-built module (lam.lot). | IP, source access, licensing and upgrade path to future Odoo versions unclear. | Get source-code ownership / licence terms and upgrade commitments in the MSA. |  | Open
O10 | Unfilled placeholders | Cover, §1, §10.1, §10.5 | MSA date, SOW effective date, fixed fee amount in §10.1 and per diem are still '[Insert …]', while §11 states 7.39M / 7.09M. | Ambiguity on the binding amount. | Fill all placeholders before signing. |  | Open
O11 | Travel to Cebu | §8, §10.5 | 3 onsite meetings are included, but travel outside Metro Manila is billed at cost + 10%. PHI is in Cebu. | Every onsite visit may be billable. | Confirm the 3 onsite meetings include travel to Cebu. |  | Open
O12 | Training depth | §8 | Four remote train-the-trainer sessions of up to 3 hours each, for 10 workstreams. | Thin for go-live readiness. | Ask for per-workstream sessions or price extra now. |  | Open
O13 | Contracting entity | Cover, signature block | Client is Primary Group of Builders Inc.; the system is for Primary Homes Incorporated; multi-company setup is a deliverable. | Licence, data ownership and billing entity must be clear. | Confirm which entities are in scope of the multi-company structure. |  | Open
O14 | No defect-response SLAs | §6, §12 | Severity-based triage is mentioned, but no response/resolution times, including for the 90-day hypercare. | Hypercare quality not measurable. | Add Sev 1–4 response and resolution targets. |  | Open