## README
PHI Odoo 19 — SOW vs Blueprint Matching
Purpose | Checks whether the vendor SOW covers PHI's ERP requirements as defined in the Enterprise Process Blueprint (SIPOC + data & interconnection matrix).
SOW reviewed | Achieve Without Borders SOW S343096, Odoo v19 Enterprise, vendor-signed 24 Sep 2026 — 739 person-days, PHP 7,090,000 ex-VAT after discount.
Blueprint basis | PHI Enterprise Process Blueprint Rev. C — 21 processes, 34 hand-off steps.
Sheets | SOW Gap Analysis · Step Matching · SOW Scope Map · SOW Effort Check · SOW Observations
Ratings | Covered = SOW clearly delivers it · Partial = some of it, gaps listed · Not covered = absent.
Yellow cells | For PHI owner responses, vendor responses and status. Everything else is the analysis.
Example input | Gap 12 → PHI owner response: "Maceda computation is mandatory at go-live"; Vendor response: "Will add to Finance Core, +8 md"; Status: Change request.
Blue figures | Typed directly from the SOW. Black figures are formulas.
Caveat | Coverage ratings are PHI's reading of the SOW text and must be confirmed with the vendor. Contract observations are for discussion with PHI Legal and are not legal advice.
Deferred scope | Leasing (10) and property management / HOA (18) are deferred to a later phase by PHI decision; they stay in the blueprint but are excluded from the SOW negotiation.

## SOW Gap Analysis
Gap analysis — blueprint (SIPOC + data matrix) vs vendor SOW
Rating: Covered = SOW clearly delivers it · Partial = some of it, gaps listed · Not covered = absent. Yellow columns are for PHI and vendor responses.
Summary
Covered | 8
Partial | 12
Not covered | 1
High-priority gaps (processes) | 8
Processes assessed | 21
Deferred to next phase | 2
Proc ID | Process | Blueprint requirement | Coverage rating | SOW coverage (section / item) | Gaps and missing scope | Priority | Recommended action | Matrix steps affected | SOW items mapped | Dev-days touching process* | PHI owner response | Vendor response | Status
01 | Budget setup (corporate & project) | Corporate + life-of-project budgets by phase and cost code; budget cycle (prepare → consolidate → ManCom approval → lock); budget check on PR/PO/bill; realignment | Partial | §3.1 G Finance Core (corporate & department budget, burn-rate; TORC budget rule builder; project P&L; budget vs actual) | No budget preparation / consolidation / approval workflow or versioning; no multi-year project budget or re-baseline; budget check at PR/PO stage not stated (only TORC dispensing). | High | Clarify in BRD: budget cycle workflow, versions, PR/PO budget check. Price as CR if not in base. | 01.1, 01.2, 01.3 | 0 | 0 |  |  | Open
02 | Corporate & project financing | Loan drawdown, allocation to projects, interest accrual and capitalization, debt service | Partial | §3.3 #99–100 Company Loans (payment processing, schedule view, cash-flow forecast link) | Debt service covered. Drawdown allocation per project, interest capitalization to project cost (and stop at completion), covenant tracking not mentioned. | Medium | Add allocation + capitalized-interest rules to BRD; confirm with Finance. | 02.1 | 2 | 12.96 |  |  | Open
03 | Corporate expenses | Request → budget check → PO/contract → receipt → bill → AP for corporate spend | Covered | §3.1 F Non-project payments (same approval & posting pipeline); §3.2 Purchase, Accounting | Petty cash / reimbursements (Odoo Expenses) not mentioned. | Low | Confirm Expenses app is in scope or handled manually. | 03.1 | 0 | 0 |  |  | Open
04 | Land acquisition | Due diligence, agreements, milestone payments, taxes and title transfer, land bank | Covered | §3.1 C Land Acquisition; D Land banking register & carrying costs; §3.3 #1–4, 12, 16–26, 29–30, 56–63, 86–87 | Strong coverage (multi-owner, DOAS, BIR/LGU filing tracker, land bank). JV with landowner paid in units (non-cash allocation) not mentioned; CARP/heirs flags depend on DD checklist content. | Medium | Confirm JV / land-for-units treatment in Discovery. | 04.1, 04.2, 04.3 | 30 | 171.36 |  |  | Open
05 | Project setup & project financing | Project master, phases/WBS, analytic account, permits (DP, ECC, BP, CR/LTS); block selling without LTS | Partial | §3.1 C Project Setup Wizard, launch readiness gate; D Land bank → project conversion; §3.3 #6–15, 37, 62, 70 | No explicit permit / License to Sell tracker; 5-criteria launch gate is land-oriented (title, payments, construction) — LTS not listed as a criterion. Wizard Step 1 (Info) is in §3.1 but not itemized in §3.3. | High | Add LTS / DHSUD permits as a launch-gate criterion and permit register. Ask why Step 1 is unpriced. | 05.1 | 15 | 77.76 |  |  | Open
06 | Project expenses & construction (milestone-based) | Contract award, progress billing with retention and DP recoupment, variation orders, % completion, POC link | Partial | §3.1 B Subcontractor billing workflow; F Contracts & deliverables (milestones, retention); D construction schedule, cost ledger; §3.3 #66–69 | Retention and milestone release covered. DP recoupment, variation orders, liquidated damages, back-charges not mentioned. BOQ listed in §3.2 but no build item. % completion does not feed revenue recognition (see C1). | High | Walk vendor through 06.1 exceptions; get written coverage or CR price. | 06.1 | 6 | 31.68 |  |  | Open
07 | Inventory & financing options setup | Lot as unit master, pricing and escalation, construction + sales status, financing schemes and payment terms | Covered | §3.1 D Inventory (Lot master, pricing floor, governed status workflow); H pricing rules engine; §3.3 #5, 16, 27–28, 69, 73 | Lot model (lam.lot) is built around block/lot land parcels. Condo units (tower-floor-unit), parking slots and house-and-lot packages not addressed. Pag-IBIG not listed among pricing schemes in H (only in Customer Loans). | High | Confirm the Lot model handles vertical projects before sign-off. | 07.1, 07.2 | 7 | 36 |  |  | Open
08 | Sales channel accreditation | Broker/agent accreditation, PRC/DHSUD/TIN docs, validity, commission scheme | Covered | §3.1 E Partner & accreditation; §3.3 #40, 48–49, 55, 64 | Expiry alerts included. Agent moving firms mid-deal not explicit. | Low | Confirm in BRD. | 08.1 | 5 | 24.48 |  |  | Open
09 | Sales (reservation to contract to sell) | Sales computation, reservation, document & credit check, CTS generation and notarization, payment schedule, revenue recognition | Partial | §3.1 H Reservation; E Sales; A buyer docs (OCR); §3.3 #31–39, 50–52, 54 | Reservation → SO flow is strong. No Contract to Sell (CTS) document template, signing and notarization tracking — the SO stands in for the contract. No credit-evaluation step. Discount approval implied, not explicit. | High | Add CTS generation (template, e-sign/notarization status) and credit check to scope. | 09.1, 09.2, 09.3 | 15 | 92.16 |  |  | Open
10 | Leasing | Lease term sheet, contract, recurring rent/CUSA billing, deposits, renewals | Not covered | None | Leasing is absent from the SOW. | Medium | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | 10.1 | 0 | 0 |  |  | Deferred (next phase)
11 | Accounts monitoring (documentation, receipting, collection) | Buyer documents, BIR-compliant receipting, collection posting and allocation, SOA, penalties, aging, demand letters | Partial | §3.1 I Customer Loans (allocation, statements, aging); J Customer Servicing (SOA); §3.3 #34, 39, 74–77, 95, 97–98 | Allocation (penalty → interest → principal), SOA, grace period and aging covered. PDC warehousing and bounced checks, demand-letter generation and BIR-registered invoice/receipt series not mentioned. | High | Add PDC management and demand letters; confirm BIR invoice series (see C2). | 11.1, 11.2, 11.3 | 15 | 86.4 |  |  | Open
12 | Cancellations & return to inventory | Maceda-compliant cancellation: grace, notarial notice, cash surrender value, refund/forfeiture, reversals, return to inventory | Partial | §3.3 #36 (SO cancel releases lot), #43 (commission clawback), H reservation cancel/release | Only the inventory release and commission clawback are covered. No RA 6552 cash-surrender-value computation, notice tracking, refund processing, forfeiture income or AR/revenue reversal. | High | Add a cancellation workflow with Maceda calculator as base scope, not CR — it is a statutory requirement. | 12.1 | 1 | 7.2 |  |  | Open
13 | Bank / Pag-IBIG takeout & in-house financing | Bank/Pag-IBIG takeout tracking (requirements, LOG/NOA, release, proceeds) and in-house financing | Partial | §3.1 I Customer Loans & Financing; B turnover aging uses takeout status; §3.3 #39, 96–98 | IHF is well covered (amortization, restructuring, compounding). Takeout workflow — requirements checklist, submission, LOG/NOA, title annotation, proceeds release, Pag-IBIG buyback — is only implied via a takeout status. | High | Specify takeout tracker fields and stages in BRD. | 13.1, 13.2 | 4 | 28.8 |  |  | Open
14 | TORC – taxes and other related charges | TORC = taxes and other related charges on title transfer: compute, fund, pay agencies, liquidate, recharge to buyer | Partial | §3.1 F Project payments (TORC): budget vs actual per project/lot; G TORC budget rule builder & dispensing engine | The SOW treats TORC as a project budget-dispensing mechanism. Buyer-side taxes and charges, recharge to buyer ledger and liquidation of cash advances are not described. Definitions may not match. | High | Align the TORC definition with the vendor in writing before BRD. | 14.1 | 0 | 0 |  |  | Open
15 | Unit preparation & delivery | Buyer turnover eligibility, joint inspection, punch list, acceptance, keys, warranty | Covered | §3.1 B turnover aging; §3.3 #72, 79, 85 (turnover & dual signatures, portal move-in status, defect tickets) | Warranty period tracking not mentioned. Note: 'Turnover' in §3.3 #70–73 means the internal land → sales hand-off, not buyer turnover. | Medium | Keep the two meanings of 'turnover' separate in the BRD glossary. | 15.1 | 7 | 41.76 |  |  | Open
16 | Accounts payable processing | Invoice capture, 3-way match, approval (DOA), EWT, payment, BIR 2307 | Covered | §3.1 F Supplier & payments (approval matrix, roll-up, retention, T-7 alerts); §3.3 #45, 59–60 | EWT named in objectives; BIR 2307 / SAWT / QAP / alphalist outputs not listed explicitly. | Medium | Confirm PH localization outputs (see C2). | 16.1, 16.2 | 4 | 27.36 |  |  | Open
17 | Commissions & sales incentives | Commission accrual, tranche release, splits, EWT, clawback, non-cash incentives | Covered | §3.1 A, E compensation engine & payout; §3.3 #41–47, 53, 91 | Well covered, including vesting, clawback and disputes. | Low | None. | 17.1 | 9 | 61.92 |  |  | Open
18 | Property management | Homeowner onboarding, dues billing and collection, servicing, PM expenses, HOA turnover | Partial | §3.3 #81–84 Helpdesk (servicing only) | Only servicing tickets are covered. Association dues billing/collection, HOA fund accounting and HOA turnover are absent. | Medium | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | 18.1, 18.2, 18.3 | 4 | 24.48 |  |  | Deferred (next phase)
19 | Title delivery | Buyer title transfer: DOAS, taxes/fees, eCAR, new TCT/CCT, release to buyer or bank | Partial | §3.1 A title status integration (Pre-BIR → Title Release); §3.3 #29 Title tab, #78 portal documents | Status visibility is covered. The processing workflow (documents, fee payment, eCAR, RD transfer, release to lender) is not itemized — the BIR/LGU filing tracker (#26) is for land acquisition. | Medium | Extend #26 filing tracker to buyer title transfer. | 19.1 | 2 | 10.08 |  |  | Open
X1 | Forecasts | Rolling sales, collection, cost-to-complete and cash forecasts | Partial | §3.1 G company performance report (cash-flow projections); §3.3 #100 cash-flow forecast link | Cash-flow projection mentioned. Sales and collection forecasts and cost-to-complete not described. | Low | Define forecast outputs in BRD. | X1.1 | 1 | 4.32 |  |  | Open
X2 | KPIs & variance reports | Budget vs actual and KPI reporting across processes | Covered | §3.1 G Finance BI; many dashboards (§3.3 #1–6, 86–91) | Well covered. | Low | None. | X2.1 | 7 | 38.88 |  |  | Open
* Items that touch several processes are counted in each, so this column does not sum to the SOW total.
Cross-cutting gaps
Ref | Topic | SOW reference | Coverage rating | Gap | Recommended action | Priority | PHI owner response | Vendor response | Status
C1 | Revenue recognition (PFRS 15, over-time / % of completion) | Not in SOW | Not covered | No mention of revenue recognition, POC journals or significant financing component — central to a developer's financials. | Add to Finance Core; agree method with external auditor first. | High |  |  | Open
C2 | BIR compliance detail | Objectives mention EWT and BIR; §9 excludes non-PH filings | Partial | CAS permit / registered invoice series, EOPT invoicing rules, e-invoicing (EIS), 2307, SAWT, QAP, alphalist and VAT on real property thresholds are not itemized. | Get a written list of PH statutory outputs delivered. | High |  |  | Open
C3 | Data migration from In4 Velocity | §3.4 data migration; §7 CSV Rule; §9 excludes history beyond cut-off | Partial | Only templated master data and opening balances. Maceda computations need full payment history (years paid); commission and takeout status also need history. | Agree cut-off and which buyer-ledger history migrates; size it now, not as flex. | High |  |  | Open
C4 | Vertical / condo projects in the Lot model | §3.1 D, §8 (existing Lot model 'stable and documented') | Partial | Lot model is land-lot based (block/lot, TCT). CCT titles, tower-floor-unit, parking not addressed. | Confirm project mix and model design. | High |  |  | Open
C5 | Existing internal systems | §9 limits integrations to CSV/MT940 imports | Not covered | No data feed to PHI's existing internal systems (e.g., BI dashboards, SharePoint document stores). | List systems that must read Odoo data; decide API vs export. | Medium |  |  | Open
C6 | Mockups referenced but not attached | §3.3 'based on the Mockups' | Partial | Scope items are defined by mockups that are not part of the SOW; items #62–64 have no description at all. | Attach mockups as an SOW annex; describe #62–64. | Medium |  |  | Open
In the SOW but not yet in the blueprint (update the blueprint)
# | SOW capability | Blueprint process(es) | Suggested blueprint update
S1 | Buyer self-service portal (SOA, payments, documents, concerns, turnover status) | 11, 15, 19 | Add portal as a channel in SIPOC for 11 and 15
S2 | Broker / agent portal (listings, lead registration, reservation requests, commission view) | 08, 09, 17 | Add as a channel in 08 and 09
S3 | Supplier accreditation workflow and performance rating | 03, 06, 16 | Add supplier accreditation as a step in procure-to-pay
S4 | Land banking register, carrying cost ledger and conversion to project | 04, 05 | Add land bank to 04 outputs and 05 inputs
S5 | 5-criteria launch readiness gate and internal land → sales turnover | 05, 07 | Add gate to diagram B before lot creation
S6 | Helpdesk with SLA, CSAT and construction punch-list | 15, 18 | Add CSAT and SLA to 15 / 18 outputs
S7 | Company loan payment processing | 02 | Already in 02 — confirm scope depth
S8 | Document OCR for buyer IDs and proof of income | 09, 11 | Add to 11.1 hand-off

## Step Matching
Step-level matching — each hand-off step against the SOW
Process rating, gaps and action are pulled from SOW Gap Analysis by formula, so updates there flow through.
Ref | Proc ID | Process | Step | Trigger event | System hand-off (blueprint) | Process coverage rating | Process gaps | Recommended action | Priority
01.1 | 01 | Budget setup (corporate & project) | Define budget structure | Budget cycle opens (timer, prior-year Q3) | Accounting › Analytic plans → Budgets; templates out to Spreadsheet | Partial | No budget preparation / consolidation / approval workflow or versioning; no multi-year project budget or re-baseline; budget check at PR/PO stage not stated (only TORC dispensing). | Clarify in BRD: budget cycle workflow, versions, PR/PO budget check. Price as CR if not in base. | High
01.2 | 01 | Budget setup (corporate & project) | Corporate budget approval | Templates issued to departments | Spreadsheet import → Budget (draft) → Approvals → Budget (confirmed) → budget check on PR/PO/bill | Partial | No budget preparation / consolidation / approval workflow or versioning; no multi-year project budget or re-baseline; budget check at PR/PO stage not stated (only TORC dispensing). | Clarify in BRD: budget cycle workflow, versions, PR/PO budget check. Price as CR if not in base. | High
01.3 | 01 | Budget setup (corporate & project) | Project (life-of-project) budget | Project approved on feasibility, or new phase launched | Project Development → Budget on project analytic → Project WBS; baseline snapshot kept for variance | Partial | No budget preparation / consolidation / approval workflow or versioning; no multi-year project budget or re-baseline; budget check at PR/PO stage not stated (only TORC dispensing). | Clarify in BRD: budget cycle workflow, versions, PR/PO budget check. Price as CR if not in base. | High
02.1 | 02 | Corporate & project financing | Loan drawdown & allocation | Loan agreement signed; approved funding requirement | Treasury → Accounting (loan liability, interest accrual) → project analytic (capitalized interest) → AP (debt-service schedule) | Partial | Debt service covered. Drawdown allocation per project, interest capitalization to project cost (and stop at completion), covenant tracking not mentioned. | Add allocation + capitalized-interest rules to BRD; confirm with Finance. | Medium
03.1 | 03 | Corporate expenses | Corporate expense request | Department need arises | Purchase request / Approvals → budget check → PO → vendor bill (16) | Covered | Petty cash / reimbursements (Odoo Expenses) not mentioned. | Confirm Expenses app is in scope or handled manually. | Low
04.1 | 04 | Land acquisition | Land due diligence | Land opportunity logged | Custom land register + Documents workspace → Approvals to ManCom | Covered | Strong coverage (multi-owner, DOAS, BIR/LGU filing tracker, land bank). JV with landowner paid in units (non-cash allocation) not mentioned; CARP/heirs flags depend on DD checklist content. | Confirm JV / land-for-units treatment in Discovery. | Medium
04.2 | 04 | Land acquisition | Land agreement & milestone payments | ManCom approval | Sign → vendor bill per milestone → AP (16) → Accounting (land held for development / advances) | Covered | Strong coverage (multi-owner, DOAS, BIR/LGU filing tracker, land bank). JV with landowner paid in units (non-cash allocation) not mentioned; CARP/heirs flags depend on DD checklist content. | Confirm JV / land-for-units treatment in Discovery. | Medium
04.3 | 04 | Land acquisition | Titling with fees | Final payment made; deed notarized | Fees → AP; TCT no. → land register and project master; land cost capitalized to project analytic | Covered | Strong coverage (multi-owner, DOAS, BIR/LGU filing tracker, land bank). JV with landowner paid in units (non-cash allocation) not mentioned; CARP/heirs flags depend on DD checklist content. | Confirm JV / land-for-units treatment in Discovery. | Medium
05.1 | 05 | Project setup & project financing | Project setup | Land titled and project budget approved | Project ↔ analytic account ↔ Budget; permit tracker; releases to unit creation (07.1) | Partial | No explicit permit / License to Sell tracker; 5-criteria launch gate is land-oriented (title, payments, construction) — LTS not listed as a criterion. Wizard Step 1 (Info) is in §3.1 but not itemized in §3.3. | Add LTS / DHSUD permits as a launch-gate criterion and permit register. Ask why Step 1 is unpriced. | High
06.1 | 06 | Project expenses & construction (milestone-based) | Construction contract & progress billing | Contract awarded; accomplishment report submitted | Purchase (contract/PO) → Project milestone % → vendor bill with retention and recoupment → AP; % completion → unit construction status and POC revenue | Partial | Retention and milestone release covered. DP recoupment, variation orders, liquidated damages, back-charges not mentioned. BOQ listed in §3.2 but no build item. % completion does not feed revenue recognition (see C1). | Walk vendor through 06.1 exceptions; get written coverage or CR price. | High
07.1 | 07 | Inventory & financing options setup | Lot master creation & pricing | Project released for sale (LTS issued) | Lot master (vendor-proposed) ↔ product and pricelist ↔ project analytic; availability board to CRM and brokers; every downstream document (reservation, CTS, ledger, turnover, title) references the Lot | Covered | Lot model (lam.lot) is built around block/lot land parcels. Condo units (tower-floor-unit), parking slots and house-and-lot packages not addressed. Pag-IBIG not listed among pricing schemes in H (only in Customer Loans). | Confirm the Lot model handles vertical projects before sign-off. | High
07.2 | 07 | Inventory & financing options setup | Financing options setup | New price list or promo scheme | Payment-term templates → sales computation (09.1) → amortization engine (11) | Covered | Lot model (lam.lot) is built around block/lot land parcels. Condo units (tower-floor-unit), parking slots and house-and-lot packages not addressed. Pag-IBIG not listed among pricing schemes in H (only in Customer Loans). | Confirm the Lot model handles vertical projects before sign-off. | High
08.1 | 08 | Sales channel accreditation | Broker / agent accreditation | Application received | Contacts (partner tags) → Documents → Approvals → commission plan; selectable on CRM / sales order | Covered | Expiry alerts included. Agent moving firms mid-deal not explicit. | Confirm in BRD. | Low
09.1 | 09 | Sales (reservation to contract to sell) | Sales computation & reservation | Buyer selects unit and scheme | CRM opportunity → sales quotation (computation) → invoice / receipt for reservation fee → unit status reserved | Partial | Reservation → SO flow is strong. No Contract to Sell (CTS) document template, signing and notarization tracking — the SO stands in for the contract. No credit-evaluation step. Discount approval implied, not explicit. | Add CTS generation (template, e-sign/notarization status) and credit check to scope. | High
09.2 | 09 | Sales (reservation to contract to sell) | CTS generation | Documents complete and DP policy met | Sales order confirmed → Sign → Documents → buyer ledger and amortization schedule (11) | Partial | Reservation → SO flow is strong. No Contract to Sell (CTS) document template, signing and notarization tracking — the SO stands in for the contract. No credit-evaluation step. Discount approval implied, not explicit. | Add CTS generation (template, e-sign/notarization status) and credit check to scope. | High
09.3 | 09 | Sales (reservation to contract to sell) | Revenue recognition | CTS signed and collectability threshold met (per policy) | Periodic journal in Accounting driven by project % complete (06.1) and collections (11.2) | Partial | Reservation → SO flow is strong. No Contract to Sell (CTS) document template, signing and notarization tracking — the SO stands in for the contract. No credit-evaluation step. Discount approval implied, not explicit. | Add CTS generation (template, e-sign/notarization status) and credit check to scope. | High
10.1 | 10 | Leasing | Lease contract & billing | Tenant accepts term sheet | Unit status leased → Rental or Subscription → recurring invoices → AR | Not covered | Leasing is absent from the SOW. | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | Medium
11.1 | 11 | Accounts monitoring (documentation, receipting, collection) | Buyer documentation | Reservation or CTS stage reached | Documents workspace linked to buyer and unit; completeness gate for CTS (09.2) and takeout (13.1) | Partial | Allocation (penalty → interest → principal), SOA, grace period and aging covered. PDC warehousing and bounced checks, demand-letter generation and BIR-registered invoice/receipt series not mentioned. | Add PDC management and demand letters; confirm BIR invoice series (see C2). | High
11.2 | 11 | Accounts monitoring (documentation, receipting, collection) | Receipting & collection posting | Payment received | Accounting payment → allocation on buyer ledger; BIR-registered invoice series (CAS / e-invoicing) | Partial | Allocation (penalty → interest → principal), SOA, grace period and aging covered. PDC warehousing and bounced checks, demand-letter generation and BIR-registered invoice/receipt series not mentioned. | Add PDC management and demand letters; confirm BIR invoice series (see C2). | High
11.3 | 11 | Accounts monitoring (documentation, receipting, collection) | SOA, delinquency & aging | Monthly cycle (timer) or due date lapsed | Follow-up reports → demand letters → collection dashboard → cancellation trigger (12.1) | Partial | Allocation (penalty → interest → principal), SOA, grace period and aging covered. PDC warehousing and bounced checks, demand-letter generation and BIR-registered invoice/receipt series not mentioned. | Add PDC management and demand letters; confirm BIR invoice series (see C2). | High
12.1 | 12 | Cancellations & return to inventory | Cancellation & refund | Buyer request, or default beyond grace | Accounting reversal (AR, revenue, commission clawback) → AP refund (16) → unit status available | Partial | Only the inventory release and commission clawback are covered. No RA 6552 cash-surrender-value computation, notice tracking, refund processing, forfeiture income or AR/revenue reversal. | Add a cancellation workflow with Maceda calculator as base scope, not CR — it is a statutory requirement. | High
13.1 | 13 | Bank / Pag-IBIG takeout & in-house financing | Bank / Pag-IBIG takeout | Equity fully paid | Takeout tracker → Titling (annotation) → Accounting (proceeds applied) → buyer balance closed | Partial | IHF is well covered (amortization, restructuring, compounding). Takeout workflow — requirements checklist, submission, LOG/NOA, title annotation, proceeds release, Pag-IBIG buyback — is only implied via a takeout status. | Specify takeout tracker fields and stages in BRD. | High
13.2 | 13 | Bank / Pag-IBIG takeout & in-house financing | In-house financing | IHF chosen and approved | Amortization schedule → monthly SOA (11.3) → interest income | Partial | IHF is well covered (amortization, restructuring, compounding). Takeout workflow — requirements checklist, submission, LOG/NOA, title annotation, proceeds release, Pag-IBIG buyback — is only implied via a takeout status. | Specify takeout tracker fields and stages in BRD. | High
14.1 | 14 | TORC – taxes and other related charges | TORC (taxes and other related charges) processing | Full payment reached / title transfer started | Titling → cash advance or bill → AP (16) → Accounting (buyer charge or project cost) | Partial | The SOW treats TORC as a project budget-dispensing mechanism. Buyer-side taxes and charges, recharge to buyer ledger and liquidation of cash advances are not described. Definitions may not match. | Align the TORC definition with the vendor in writing before BRD. | High
15.1 | 15 | Unit preparation & delivery | Turnover | Unit ready and account eligible | Field Service / Project tasks → Sign (acceptance) → unit status turned over → PM onboarding and dues (18.1) | Covered | Warranty period tracking not mentioned. Note: 'Turnover' in §3.3 #70–73 means the internal land → sales hand-off, not buyer turnover. | Keep the two meanings of 'turnover' separate in the BRD glossary. | Medium
16.1 | 16 | Accounts payable processing | AP invoice processing | Vendor bill received | Purchase ↔ bill (3-way match) → Approvals → payment batch → bank → BIR 2307 → budget actuals | Covered | EWT named in objectives; BIR 2307 / SAWT / QAP / alphalist outputs not listed explicitly. | Confirm PH localization outputs (see C2). | Medium
16.2 | 16 | Accounts payable processing | Disbursement | Approved bill falls due | Accounting → bank file or check printing → bank reconciliation | Covered | EWT named in objectives; BIR 2307 / SAWT / QAP / alphalist outputs not listed explicitly. | Confirm PH localization outputs (see C2). | Medium
17.1 | 17 | Commissions & sales incentives | Commission accrual & release | CTS signed (accrual); collection threshold reached (release) | Sales → commission computation → broker bill → AP (16); non-cash incentives via Purchase / Inventory | Covered | Well covered, including vesting, clawback and disputes. | None. | Low
18.1 | 18 | Property management | Homeowner onboarding & dues | Turnover accepted | Subscription / recurring invoices → collection → HOA fund accounting | Partial | Only servicing tickets are covered. Association dues billing/collection, HOA fund accounting and HOA turnover are absent. | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | Medium
18.2 | 18 | Property management | Servicing & PM expenses | Service request or scheduled maintenance | Helpdesk / Field Service → Purchase → AP (property-management expenses) | Partial | Only servicing tickets are covered. Association dues billing/collection, HOA fund accounting and HOA turnover are absent. | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | Medium
18.3 | 18 | Property management | HOA turnover | Turnover criteria met | Final PM accounting close → Documents | Partial | Only servicing tickets are covered. Association dues billing/collection, HOA fund accounting and HOA turnover are absent. | Deferred to a later phase by PHI decision. Not included in the vendor clarification letter; no pricing requested. | Medium
19.1 | 19 | Title delivery | Title processing & delivery | Full payment, or lender requires title for release | Title tracker → Documents → buyer notice; feeds takeout release (13.1) | Partial | Status visibility is covered. The processing workflow (documents, fee payment, eCAR, RD transfer, release to lender) is not itemized — the BIR/LGU filing tracker (#26) is for land acquisition. | Extend #26 filing tracker to buyer title transfer. | Medium
X1.1 | X1 | Forecasts | Rolling forecasts | Month-end close | All modules → Spreadsheet / dashboards | Partial | Cash-flow projection mentioned. Sales and collection forecasts and cost-to-complete not described. | Define forecast outputs in BRD. | Low
X2.1 | X2 | KPIs & variance reports | KPIs & variance reporting | Period close | Accounting budget report → dashboards / BI | Covered | Well covered. | None. | Low
Steps by rating
Covered |  | 12
Partial |  | 21
Not covered |  | 1

## SOW Scope Map
SOW §3.3 customizations mapped to blueprint processes
Source: Achieve Without Borders SOW S343096 (Odoo v19), dated 24 Sep 2026. Dev man-days transcribed as stated in the SOW.
# | Section | Feature | Dev man-days | Blueprint process(es) | Process name(s)
1 | Dashboard | Acquisition KPI Cards | 4.32 | 04 | Land acquisition
2 | Dashboard | Attention Required List | 5.76 | 04 | Land acquisition
3 | Dashboard | Project Progress Bars | 2.88 | 04 | Land acquisition
4 | Dashboard | Quick Navigation | 2.88 | 04 | Land acquisition
5 | Dashboard | Lot Inventory | 5.76 | 07 | Inventory & financing options setup
6 | Dashboard | Project | 4.32 | 05 | Project setup & project financing
7 | Projects & Pipeline | Project Consolidated View | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
8 | Projects & Pipeline | Project Search & Filters | 4.32 | 05 | Project setup & project financing
9 | Project Setup Wizard | Step 2 - Site Details | 4.32 | 05 | Project setup & project financing
10 | Project Setup Wizard | Step 3 - Targets | 4.32 | 05 | Project setup & project financing
11 | Project Setup Wizard | Step 4 - Team Assignment | 4.32 | 05 | Project setup & project financing
12 | Project Setup Wizard | Step 5 - Milestone Template | 5.76 | 04 | Land acquisition
13 | Project Setup Wizard | Step 6 - Documents | 4.32 | 05 | Project setup & project financing
14 | Project Setup Wizard | Step 7 - Review & Launch | 4.32 | 05 | Project setup & project financing
15 | Project Setup Wizard | Sample Form Previews | 4.32 | 05 | Project setup & project financing
16 | Lot Onboarding Form | Lot Master Data | 5.76 | 04, 07 | Land acquisition; Inventory & financing options setup
17 | Lot Onboarding Form | Pricing & Source | 4.32 | 04 | Land acquisition
18 | Lot Onboarding Form | Seller/Owner Details | 4.32 | 04 | Land acquisition
19 | Lot Onboarding Form | Attachments Checklist | 4.32 | 04 | Land acquisition
20 | Lot Onboarding Form | Auto Due-Diligence Checklist | 7.2 | 04 | Land acquisition
21 | Lot Onboarding Form | Approval Route | 5.76 | 04 | Land acquisition
22 | Lot Onboarding Form | Bulk Lot Onboarding Wizard | 7.2 | 04 | Land acquisition
23 | Acquisition & Payments (Multi-Owner) | Multi-Owner Land Sources | 8.64 | 04 | Land acquisition
24 | Acquisition & Payments (Multi-Owner) | Per-Owner Milestone Schedule | 8.64 | 04 | Land acquisition
25 | Acquisition & Payments (Multi-Owner) | Auto-Drafted Deed of Absolute Sale | 8.64 | 04 | Land acquisition
26 | Acquisition & Payments (Multi-Owner) | BIR / LGU Filing Tracker | 7.2 | 04 | Land acquisition
27 | Lot Detail & Lifecycle | Lot Lock / Reusable Pill | 4.32 | 07, 09 | Inventory & financing options setup; Sales (reservation to contract to sell)
28 | Lot Detail & Lifecycle | Locked Ribbon & Kanban Lock Icons | 4.32 | 07 | Inventory & financing options setup
29 | Lot Detail & Lifecycle | Title Tab | 5.76 | 04, 19 | Land acquisition; Title delivery
30 | Lot Detail & Lifecycle | DD / Milestones / Construction Tabs | 7.2 | 04, 06 | Land acquisition; Project expenses & construction (milestone-based)
31 | CRM → Reservation → Sales Order | Lot Interest & Availability Browser | 7.2 | 09 | Sales (reservation to contract to sell)
32 | CRM → Reservation → Sales Order | Reserve Lot from Opportunity | 7.2 | 09 | Sales (reservation to contract to sell)
33 | CRM → Reservation → Sales Order | Soft-Hold with Expiry (Reservation) | 7.2 | 09 | Sales (reservation to contract to sell)
34 | CRM → Reservation → Sales Order | Reservation Fee Payment & Receipt | 7.2 | 09, 11 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection)
35 | CRM → Reservation → Sales Order | Opportunity Won → Auto-Create Sales Order | 7.2 | 09 | Sales (reservation to contract to sell)
36 | CRM → Reservation → Sales Order | SO Confirm / Lot Lock Flow | 7.2 | 09, 12 | Sales (reservation to contract to sell); Cancellations & return to inventory
37 | CRM → Reservation → Sales Order | Launch-Readiness Gate on SO Confirm | 5.76 | 05, 09 | Project setup & project financing; Sales (reservation to contract to sell)
38 | CRM → Reservation → Sales Order | Double-Sell / Double-Reserve Constraint | 5.76 | 09 | Sales (reservation to contract to sell)
39 | CRM → Reservation → Sales Order | Customer Payment Schedule Generator | 8.64 | 09, 11, 13 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
40 | Broker Commission | Broker / Agent Master Record | 4.32 | 08 | Sales channel accreditation
41 | Broker Commission | Commission Plan Setup | 8.64 | 17 | Commissions & sales incentives
42 | Broker Commission | Commission Tagging on Reservation / SO | 4.32 | 17 | Commissions & sales incentives
43 | Broker Commission | Commission Computation Engine | 11.52 | 17 | Commissions & sales incentives
44 | Broker Commission | Commission Release / Vesting Rules | 7.2 | 17 | Commissions & sales incentives
45 | Broker Commission | Commission Voucher & Payout | 7.2 | 16, 17 | Accounts payable processing; Commissions & sales incentives
46 | Broker Commission | Broker Commission Statement | 5.76 | 17 | Commissions & sales incentives
47 | Broker Commission | Commission Audit & Disputes | 5.76 | 17 | Commissions & sales incentives
48 | Broker Portal | Broker Portal Login & Access | 4.32 | 08 | Sales channel accreditation
49 | Broker Portal | My Listings & Lot Availability | 5.76 | 07, 08 | Inventory & financing options setup; Sales channel accreditation
50 | Broker Portal | Register Lead / Buyer Referral | 5.76 | 09 | Sales (reservation to contract to sell)
51 | Broker Portal | Reservation Request via Portal | 7.2 | 09 | Sales (reservation to contract to sell)
52 | Broker Portal | Deal Status Tracker | 4.32 | 09 | Sales (reservation to contract to sell)
53 | Broker Portal | Commission Visibility | 5.76 | 17 | Commissions & sales incentives
54 | Broker Portal | Document Upload | 4.32 | 09, 11 | Sales (reservation to contract to sell); Accounts monitoring (documentation, receipting, collection)
55 | Broker Portal | Portal Notifications | 4.32 | 08 | Sales channel accreditation
56 | Payment Milestones & Reminders | Milestone Templates | 4.32 | 04 | Land acquisition
57 | Payment Milestones & Reminders | Lot Milestones | 5.76 | 04 | Land acquisition
58 | Payment Milestones & Reminders | Automated Payment Reminders | 7.2 | 04, 11 | Land acquisition; Accounts monitoring (documentation, receipting, collection)
59 | Payment Milestones & Reminders | Invoice Generation from Milestones | 5.76 | 04, 16 | Land acquisition; Accounts payable processing
60 | Approvals & Documents | Milestone Release Approvals | 5.76 | 04, 16 | Land acquisition; Accounts payable processing
61 | Approvals & Documents | Central Document Repository | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
62 | Approvals & Documents | Project Approval Workflow | 5.76 | 05 | Project setup & project financing
63 | Approvals & Documents | Lot Approval Workflow | 5.76 | 04 | Land acquisition
64 | Approvals & Documents | Broker Approval Workflow | 5.76 | 08 | Sales channel accreditation
65 | Approvals & Documents | Audit Logs | 4.32 | X2 | KPIs & variance reports
66 | Construction Monitoring | Progress Photo Gallery | 5.76 | 06 | Project expenses & construction (milestone-based)
67 | Construction Monitoring | Cluster Health Board | 7.2 | 06 | Project expenses & construction (milestone-based)
68 | Construction Monitoring | Cluster Alert Cron | 4.32 | 06 | Project expenses & construction (milestone-based)
69 | Construction Monitoring | Construction % to Stage | 4.32 | 06, 07 | Project expenses & construction (milestone-based); Inventory & financing options setup
70 | Launch Readiness & Turnover | 5-Criteria Launch Readiness Gate | 7.2 | 05 | Project setup & project financing
71 | Launch Readiness & Turnover | Pre-Turnover Inspection Checklist | 5.76 | 04, 05 | Land acquisition; Project setup & project financing
72 | Launch Readiness & Turnover | Turnover Inspection & Dual Signatures | 7.2 | 05, 15 | Project setup & project financing; Unit preparation & delivery
73 | Launch Readiness & Turnover | CRM / Saleable Unit Hand-off | 5.76 | 07 | Inventory & financing options setup
74 | Customer Portal | My Lots & Purchase Summary | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
75 | Customer Portal | Payment Schedule & Balance | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
76 | Customer Portal | Online Payment / Payment Submission | 8.64 | 11 | Accounts monitoring (documentation, receipting, collection)
77 | Customer Portal | Payment Reminders & Receipts | 5.76 | 11 | Accounts monitoring (documentation, receipting, collection)
78 | Customer Portal | Document Access | 4.32 | 11, 19 | Accounts monitoring (documentation, receipting, collection); Title delivery
79 | Customer Portal | Turnover & Move-In Status | 4.32 | 15 | Unit preparation & delivery
80 | Customer Portal | Profile & Contact Management | 4.32 | 11 | Accounts monitoring (documentation, receipting, collection)
81 | Helpdesk | Ticket Intake Channels | 5.76 | 15, 18 | Unit preparation & delivery; Property management
82 | Helpdesk | Ticket Categories & SLA | 5.76 | 15, 18 | Unit preparation & delivery; Property management
83 | Helpdesk | Ticket Assignment & Routing | 5.76 | 15, 18 | Unit preparation & delivery; Property management
84 | Helpdesk | Ticket Workbench | 7.2 | 15, 18 | Unit preparation & delivery; Property management
85 | Helpdesk | Defect / Punch-List Tickets | 5.76 | 15 | Unit preparation & delivery
86 | Reporting & BI | Cost vs Paid Analysis | 5.76 | 04, X2 | Land acquisition; KPIs & variance reports
87 | Reporting & BI | Milestone Aging Report | 4.32 | 04, X2 | Land acquisition; KPIs & variance reports
88 | Reporting & BI | Summary Reports (PDF/XLSX) | 7.2 | X2 | KPIs & variance reports
89 | Reporting & BI | Audit / Status Reports | 5.76 | X2 | KPIs & variance reports
90 | Reporting & BI | Customer (BI and Report) | 5.76 | 11, X2 | Accounts monitoring (documentation, receipting, collection); KPIs & variance reports
91 | Reporting & BI | Broker (BI and Report) | 5.76 | 17, X2 | Commissions & sales incentives; KPIs & variance reports
92 | Configuration & Settings | Reminder Offsets | 2.88 | 04, 11 | Land acquisition; Accounts monitoring (documentation, receipting, collection)
93 | Configuration & Settings | Cluster Thresholds | 2.88 | 06 | Project expenses & construction (milestone-based)
94 | Configuration & Settings | SO Gating Toggle | 2.88 | 09 | Sales (reservation to contract to sell)
95 | Configuration & Settings | Grace Period | 2.88 | 11 | Accounts monitoring (documentation, receipting, collection)
96 | Customer Loans | Customer Loan Configuration | 7.2 | 13 | Bank / Pag-IBIG takeout & in-house financing
97 | Customer Loans | Automated Customer Loan Payment Processing | 8.64 | 11, 13 | Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
98 | Customer Loans | Customer Payment Schedule List View | 4.32 | 11, 13 | Accounts monitoring (documentation, receipting, collection); Bank / Pag-IBIG takeout & in-house financing
99 | Company Loans | Automated Company Loan Payment Processing | 8.64 | 02, 16 | Corporate & project financing; Accounts payable processing
100 | Company Loans | Company Loan Schedule List View | 4.32 | 02, X1 | Corporate & project financing; Forecasts
Total itemized dev man-days |  |  | 573.12
Section subtotal check
| Section | SOW stated subtotal | Computed from items | Difference
| Dashboard | 25.92 | 25.92 | 0
| Projects & Pipeline | 10.08 | 10.08 | 0
| Project Setup Wizard | 31.68 | 31.68 | 0
| Lot Onboarding Form | 38.88 | 38.88 | 0
| Acquisition & Payments (Multi-Owner) | 33.12 | 33.12 | 0
| Lot Detail & Lifecycle | 21.6 | 21.6 | 0
| CRM → Reservation → Sales Order | 63.36 | 63.36 | 0
| Broker Commission | 54.72 | 54.72 | 0
| Broker Portal | 41.76 | 41.76 | 0
| Payment Milestones & Reminders | 23.04 | 23.04 | 0
| Approvals & Documents | 33.12 | 33.12 | 0
| Construction Monitoring | 21.6 | 21.6 | 0
| Launch Readiness & Turnover | 25.92 | 25.92 | 0
| Customer Portal | 38.88 | 38.88 | 0
| Helpdesk | 30.24 | 30.24 | 0
| Reporting & BI | 34.56 | 34.56 | 0
| Configuration & Settings | 11.52 | 11.52 | 0
| Customer Loans | 20.16 | 20.16 | 0
| Company Loans | 12.96 | 12.96 | 0
| Total | 573.12 | 573.12 | 0
Blue = figures typed from the SOW. Differences of 0.00 mean the SOW section subtotals add up.

## SOW Effort Check
SOW §5.1 effort table — arithmetic and capacity check
Figures typed from §5.1 in blue. As printed, the Dev Lead column carries more days than Developer; ask the vendor to confirm.
Workstream | Lead Functional Consultant | BA | Dev Lead | Developer | QA | Infra | SOW stated total | Computed total | Difference
CRM, Buyer & Agent Portal | 10 | 7 | 29 | 10 |  |  | 56 | 56 | 0
Construction Monitoring | 6 | 5 | 19 | 6 |  |  | 36 | 36 | 0
Land Acquisition | 10 | 7 | 31 | 10 |  |  | 58 | 58 | 0
Inventory Management | 10 | 7 | 31 | 10 |  |  | 58 | 58 | 0
Sales Management & Commissions | 10 | 7 | 29 | 10 |  |  | 56 | 56 | 0
Supplier & Payments | 8 | 6 | 27 | 8 |  |  | 49 | 49 | 0
Finance Core & TORC Budget | 10 | 7 | 26 | 10 |  |  | 53 | 53 | 0
Reservation Management | 7 | 6 | 22 | 7 |  |  | 42 | 42 | 0
Customer Loans & Financing | 7 | 12 | 37 | 10 | 7 |  | 72 | 73 | 1
Customer Servicing Portal | 6 | 5 | 17 | 6 |  |  | 34 | 34 | 0
Data Migration, UAT & Training | 12 | 5 | 14 | 14 | 10 |  | 55 | 55 | 0
Infrastructure, Environments & Cutover |  |  | 3 |  |  | 29 | 32 | 32 | 0
Project Management & Governance | 48 | [5 empty] | 48 | 48 | 0
Hypercare (90 days post go-live) | [6 empty] | 90 | 90 | n/a (not split by role)
Total | 144 | 74 | 285 | 101 | 17 | 29 | 739 | 740 | 1
Capacity vs itemized build
Development capacity in §5.1 (Dev Lead + Developer) | 386
Itemized §3.3 customization dev man-days | 573.12
Shortfall (itemized minus capacity) | 187.12
Shortfall as % of itemized | 32.65%
§3.1 lists further features that have no §3.3 line (land banking, supplier module, TORC budget, project P&L), so the real gap is larger than shown.

## SOW Observations
Commercial and contract observations on the SOW
For discussion with the vendor and PHI Legal before signature. Not legal advice.
# | Observation | SOW reference | Finding | Impact on PHI | Suggested ask | Owner | Status
O1 | Build effort vs itemized scope | §3.3 vs §5.1 | The 100 itemized customizations total 573.12 dev-days. The two development columns in §5.1 (Dev Lead + Developer) total only 386 person-days, and §3.1 adds features not in §3.3 (land banking, supplier module, TORC budget, project P&L). | Scope looks under-resourced by roughly a third; risk of rushed build or later change orders. | Ask the vendor to reconcile, and confirm in writing that every §3.1 and §3.3 item is inside the Fixed Base Fee. |  | Open
O2 | §5.1 columns look swapped | §5.1 | As printed, Dev Lead carries 285 days and Developer 101 — the reverse of what a normal team shape would be. | Unclear team composition. | Ask for the corrected table and named roles. |  | Open
O3 | Arithmetic error: Customer Loans row | §5.1 | 7 + 12 + 37 + 10 + 7 = 73, but the row total says 72. The grand total of 739 uses 72. | Minor, but signals the table wasn't checked. | Ask for a corrected table. |  | Open
O4 | Payment gateway: in scope and out of scope | §3.3 #76 vs §9 | Item #76 (8.64 dev-days) builds online payment via gateway, while §9 lists payment gateway integration as out of scope. | PHI may pay for #76 and again for a CR. | Resolve: either remove #76's gateway part from the fee or remove it from §9. |  | Open
O5 | Two man-day rates | Cover page vs §10.2 | Base effort priced at PHP 10,000/day (739 × 10,000 = 7.39M); flex, overages and replenishments at PHP 12,000/day. | Gaps found in this analysis would be priced at the higher rate. | Negotiate the gap items into base scope before signing, or lock CRs at 10,000. |  | Open
O6 | Front-loaded billing | §11 | 50% (PHP 3.695M) is billed by BRD sign-off, before any build; 80% before go-live. | Reduced leverage if build quality slips. | Consider moving part of milestone 1 to SIT completion. |  | Open
O7 | Deemed acceptance | §11, §12 | Deliverables are accepted after 5 working days without written objection, and joining a later phase accepts the earlier one. | Short review window across 10 workstreams. | Extend to 10 working days, or name reviewers per deliverable in the RACI. |  | Open
O8 | Flex allocation is small | §10.3 | 35 person-days total; only 10 for change orders (PHP 120,000 at 12,000). | The High-priority gaps here will exceed it quickly. | Size the gaps now and add them to base scope. |  | Open
O9 | Lot model ownership | §8 | Assumes 'the existing custom Lot model' is stable and documented — suggests a vendor-owned pre-built module (lam.lot). | IP, source access, licensing and upgrade path to future Odoo versions unclear. | Get source-code ownership / licence terms and upgrade commitments in the MSA. |  | Open
O10 | Unfilled placeholders | Cover, §1, §10.1, §10.5 | MSA date, SOW effective date, fixed fee amount in §10.1 and per diem are still '[Insert …]', while §11 states 7.39M / 7.09M. | Ambiguity on the binding amount. | Fill all placeholders before signing. |  | Open
O11 | Travel to Cebu | §8, §10.5 | 3 onsite meetings are included, but travel outside Metro Manila is billed at cost + 10%. PHI is in Cebu. | Every onsite visit may be billable. | Confirm the 3 onsite meetings include travel to Cebu. |  | Open
O12 | Training depth | §8 | Four remote train-the-trainer sessions of up to 3 hours each, for 10 workstreams. | Thin for go-live readiness. | Ask for per-workstream sessions or price extra now. |  | Open
O13 | Contracting entity | Cover, signature block | Client is Primary Group of Builders Inc.; the system is for Primary Homes Incorporated; multi-company setup is a deliverable. | Licence, data ownership and billing entity must be clear. | Confirm which entities are in scope of the multi-company structure. |  | Open
O14 | No defect-response SLAs | §6, §12 | Severity-based triage is mentioned, but no response/resolution times, including for the 90-day hypercare. | Hypercare quality not measurable. | Add Sev 1–4 response and resolution targets. |  | Open